## W04
Domestic Homicide Reviews - W04 - Actions Log
CSP | DHR Ref | Recommendations | Primary Lead Agency | Narrative/Update | Evidence of Achievement (Output/Outcome)
South Warwickshire | W04 | Coventry and Warwickshire Clinical Commissioning Group, Coventry and Warwickshire Partnership Trust and South Warwickshire NHS Foundation Trust assure the Safer South Warwickshire Community Safety Partnership that the recommendation of the SWP DV Strategic Review, i.e. that Routine Enquiry into Domestic Abuse is embedded into training, policy and procedure. | ICB / CWPT / SWFT | Review and make recommendations re REFUGE training delivery package for all professionals, to also include Routine enquiry and DASH risk assessment. Review and revise ICB training package to Primary Care to also include Routine enquiry and DASH risk assessment. Consider undertaking a Routine enquiry audit Liaison with REFUGE to ensure Primary care updates are issued across Warwickshire A. Present DHR summary and lessons learnt at Protected Learning time event, highlighting key areas. B. Present DHR summary and lessons learnt at SG Lead GP forums. C. Consider Pre recording of DHR summary and lessons learnt for wider distribution | ALL ACTIONS COMPLETED: April 2021 DASH training became an essential skill for any staff who work clinically. They are recommended to complete the relevant training that incorporates routine enquiry into Domestic Abuse. June 2024 Update : A Trainer from SARC (Sexual Assault Referral Centres) will attend PLT to update staff on services and response to disclosures to support victims. Completed. Completed September 2022. Completed. Presentation in Protected Learning Time event September 2022-register of attendees. Scheduled in Summer 2023 and wider audience to be reached via C. New target date April 2024
South Warwickshire | W04 | Warwickshire Safeguarding Adults’ Board to consider a means and seek assurance from other Warwickshire faith based groups that they have written structured Safeguarding Policies. | Warwickshire Safeguarding Adults Board | Nov 2023: Completed and ongoing. The Business Manager has met with the Chair of the Faith Forum to scope the level of support required for the development of safeguarding policy and procedures for Warwickshire's faith based groups. WSEB have agreed that Early Help will be the next topic covered for the annual thematic review, WSP will consider the best way to gain assurances from faith organisations as part of any ongoing quality assurance work. | COMPLETED: Thematic review reports. Minutes from WSEB.
South Warwickshire | W04 | South Warwickshire Community Safety Partnership Board ensures that the Charity Commission be provided with a copy of this Domestic Homicide Review. | Warwickshire Safeguarding Adults Board |  | COMPLETED: November 2024
South Warwickshire | W04 | To work in conjunction with the clinical audit department to assess the quality of the electronic record keeping. This will be carried out by enquiring what Record Keeping audits are in place and how they may include quality and analysis of note keeping. | SWFT | To find out what record keeping audits are in place and how they ensure quality and analysis of note keeping. | COMPLETED: 14.08.20 Audit Team have been contacted and this action is now closed and completed
South Warwickshire | W04 | To work with Operational Managers within DN services and Podiatry and the training department to offer Domestic Abuse and DASH safeguarding training appropriate for their role in adherence with Adult Safeguarding Roles and Competencies for Healthcare Staff, 2018. This will be as part of the training for all health professionals within the Trust. | SWFT | Arrange the delivery of DA and DASH training. | COMPLETED: DASH training is in place and rolling programme of delivery is ongoing. Several meetings to discuss and plan a multiagency package has taken place with CWPT and future dates are in place to finalise a teaching package
South Warwickshire | W04 | To write a Multi-agency training package across the Health Economy to consider Older Adult Domestic Abuse. | SWFT | To contact the district nurses managers and review if DA and DASH training is occurring. Provide reassurance that the training package considers older adult DA | COMPLETED: Training package for older adults and domestic abuse was written together with CWPT and is now being delivered. Completed. January 2021