Warwickshire County Council

Minerals and Waste Development Scheme

2005 – 2008

November 2006

Contents

|  | Section |  |
| --- | --- | --- |
|  | Summary |  |
| 1 | Introduction |  |
| 2 | Relationship with Existing Planning Policy Documents |  |
|  | - Regional Spatial Strategy |  |
|  | - “Saved” plans |  |
| 3 | Proposed Local Development Documents |  |
|  | - The evidence base of the Minerals and Waste Development Framework |  |
|  | - Sustainability Appraisal |  |
|  | - Annual Monitoring Report |  |
| 3 | Supporting Statement |  |
|  | - Political management of the Minerals and Waste Development Framework |  |
|  | - Delivering the Local Development Scheme – What could go wrong? |  |
|  | - Contact details |  |
|  | Appendices |  |
|  | Appendix 1: Schedule of proposed Local Development Documents |  |
|  | Appendix 2: Programme Management of Local Development Documents |  |
|  | Appendix 3: Profile of each Local Development Document |  |
|  |  | Statement of Community Involvement |
|  |  | Waste Core Strategy |
|  |  | Waste Allocations DPD |
|  |  | Minerals Core Strategy |
|  |  | Minerals Allocation DPD |
|  |  | Proposals Map |
|  | Appendix 4: Diagram showing the relationship between the Local Development Documents and other Development Plan Documents |  |
|  | Appendix 5 : Schedule of Replacement of Minerals and Waste Local Plan ‘Saved’ Policies |  |

Summary

This Minerals and Waste Development Scheme (MWDS) is a critical part of the Minerals and Waste Development Framework (MWDF), giving an opportunity for the County to set out its current planning policies and to explain to the local community those plans and policies that it proposes to prepare over the next three years.  The document covers the period 2005 – 2008. It identifies key milestones in the preparation of mineral and waste development documents, which will be project managed and subject to continuous review. The MWDS has been formally approved by the County Council and submitted to the Secretary of State. Should there be no objections raised by him within 28 days of submission it comes into effect.

The County is required to produce an MWDS under the Planning & Compulsory Purchase Act 2004.  The Act requires local planning authorities to prepare a new series of planning documents which together make up a “Minerals and Waste Development Framework” (MWDF).  One of the roles of this MWDS is to explain how the various constituent that make up the MWDF fit together.

The key priorities for Warwickshire County Council over the three year period 2005-2008 are as follows:-

| Document | Comment |
| --- | --- |
| Statement of Community Involvement | This document outlines the standards and approach that the County will undertake in involving stakeholders and the local community in producing all its LDDs. |
| Waste Core Strategy | This will set a long term vision, objectives and strategy for waste development across the County up to 2021, and provide the framework for waste development control. |
| Waste Allocations DPD | This will provide detailed allocations for waste related development and criteria based policies where this is not possible. |
| Minerals Core Strategy | This will set a long term vision, objectives and strategy for mineral development across the County up to 2021, and provide the framework for mineral development control. |
| Minerals Allocations DPD | This will provide detailed allocations for mineral related development and criteria based policies where this is not possible. |
| Proposals Map | This will illustrate the policies set out in all development plan documents. |

This MWDS explains how these documents will be prepared, including outlining when community and stakeholder involvement will be sought.  It also explains what will be the role, relationship and status of other existing planning documents, including the Warwickshire Structure Plan, the District’s Development Documents and the Regional Spatial Strategy.

1.	Introduction

1.1	This Minerals and Waste Development Scheme (MWDS) has been prepared to give the local community and all interested parties information on two important areas:-

- What are the current mineral and waste planning policies that are being applied to Warwickshire  County, and

- What is the programme for reviewing these policies to provide updated policies for the County.

1.2	The County Council is required to produce a MWDS under the terms of the Planning & Compulsory Purchase Act 2004.  The legislation and accompanying regulations and guidance from Government give a framework within which the County Council must operate as it prepares this document.   The MWDS identifies the first three-years programme of work, but also indicates in general terms what work is proposed beyond the three year period. It identifies key milestones in the preparation of mineral and waste development documents, which will be project managed and subject to continuous review. It must also be submitted to the Secretary of State, and should there be no objections raised by him within 28 days of submission it comes into effect.

  - In producing this MWDS, the County Council is committed to the following:-

- To make the Minerals and Waste Development Scheme as clear to understand as possible,

- To publish the Minerals and Waste Development Scheme on the Council’s web site (www.warwickshire.gov.uk/planning).

  - Although this MWDS will be reviewed annually, the County Council may, from time to time, need to update it more frequently.  This may happen if, for example, circumstances require the preparation of a Supplementary Planning Document (SPD) or there is a sudden change in circumstances requiring an early review of an LDD.  When this happens, the County Council  will submit a revised MWDS to the Secretary of State, in consultation with the Government Office and the Planning Inspectorate (as necessary) and will publish this as an amendment to the MWDS on our web site.

2.	Relationship with existing Planning Policy Documents

2.1	This section provides an overview of the key planning documents that cover the County Council at the present time, including those prepared by other planning authorities.  In particular it gives guidance on the current state and status of documents prepared by the Regional Planning Body, as well as other planning authorities.

2.2	However, before setting the context, it is important to understand how the various documents relate to one another, and what their status is.  This is particularly important given the recent changes in legislation, and the fact that County Council has current planning policy prepared under the previous legislative framework. The key terms used within this Scheme are as follows:-

| Document |  | Definition |
| --- | --- | --- |
| Waste Local plan | WLP | Detailed statutory land use plan produced by the County Council setting out specific policies and proposals to be applied to Planning Applications for waste management facilities such as landfill sites, incinerators and recycling depots. |
| Minerals Local Plan | MLP | Detailed statutory land use plan produced by the County Council setting out specific policies and proposals to be applied to planning applications for mineral workings. |
| Minerals and Waste Development Framework | MWDF | A folder containing all LDD’s and therefore all planning policies applying within the County. |
| Local Development Document | LDD | The generic name given to all documents that make up the MWDF. These include both DPD’s and SPD’s. The role of LDDs is to set out the spatial strategy and planning policies for the County. |
| Development Planning Document | DPD | These are documents that have been subject to independent testing and have the weight of development plan status. They are effectively the successor to the present local plan. |
| Minerals and Waste Development Scheme | MWDS | The project plan for the preparation of the MWDF. |
| Statement of Community Involvement | SCI | A statement setting out how communities and stakeholders will be involved in the process of producing LDDs. |
| Structure Plan | SP | The present strategic plan for Warwickshire. |
| Regional Spatial Strategy | RSS | The strategic plan produced at a regional level for the West Midlands. This is a statutory plan and will form the basis for preparing LDDs. It is prepared by the West Midlands Regional Assembly acting in their role as the Regional Planning Body for the West Midlands. |
| Annual Monitoring Report | AMR | The report prepared by the County Council to assess the implementation of the MWDS and the extent to which the policies in the MWDF are being achieved. |

The Regional Spatial Strategy

2.3	The regional context for planning within the County is provided by the Regional Spatial Strategy.  Regional Planning Guidance for the West Midlands for the period to 2011 was approved by the Secretary of State in 1998.  Since that time the West Midlands Local Government Association has been working on producing a new Regional Planning Guidance to provide a framework for the West Midlands up to 2021.  Since April 2003, this work has now been taken over by the West Midlands Regional Assembly.  Regional Planning Guidance was approved by Government in June 2004. With the commencement of the Planning and Compulsory Purchase Act 2004, it became the Regional Spatial Strategy for the West Midlands.  As such it has statutory status.  It is therefore has development plan status and future LDD’s will be required to be in general conformity with it.

Saved Plans

2.4	“Saved” plans are those prepared under previous legislation but which are permitted to retain their previous status for a three year period after the commencement of the new Planning Act, i.e. until September 2007. The Minerals and Waste Local Plans will be ‘saved’ for three years, and will be progressively replaced by DPDs within the MWDF. If necessary a case will be made in subsequent MWDS to save certain policies beyond September 2007.  There are a number of ‘saved’ plans that affect the County:-

2.5	The Warwickshire Structure Plan was adopted in 2001 and will be “saved” until September 2007 except for those parts that are not in conformity with the RSS.

2.6	The Minerals Local Plan for Warwickshire were adopted by Warwickshire County Council in 1995, and will be “saved” until September 2007.  The Local Plan will be progressively replaced by LDD’s which will have the status of Development Plan Documents.

2.7	The Waste Local Plan for Warwickshire was adopted by the County Council in 1999, and will be ‘saved’ until September 2007. The Local Plan will be progressively replaced by LDD’s which will have the status of Development Plan Documents.

3.0	Proposed Local Development Documents

3.1	Much of the rest of this MWDS considers in more detail the new LDDs that the Council proposes to prepare. The key priorities for Warwickshire County Council over the three year period 2005-2008 are as follows:-

| Document | Comment |
| --- | --- |
| Statement of Community Involvement | This document outlines the standards and approach that the County will undertake in involving stakeholders and the local community in producing all its LDDs. |
| Waste Core Strategy | This will set a long term vision, objectives and strategy for waste development across the County up to 2021, and provide the framework for waste development control. |
| Waste Allocations DPD | This will provide detailed allocations for waste related development and criteria based policies where this is not possible. |
| Minerals Core Strategy | This will set a long term vision, objectives and strategy for mineral development across the County up to 2021, and provide the framework for minerals development control. |
| Minerals Allocations DPD | This will provide detailed allocations for mineral related development and criteria based policies where this is not possible. |
| Proposals Map | A Submission proposals map will accompany the submission of each DPD and will illustrate all the policies set out. (it may be the case that Core Strategies may not necessitate a change to an Adopted Proposals Map). The County Council will work with the District Councils, who must include on their adopted proposals map, safeguarded areas, mineral consultation areas and any adopted minerals and waste allocations. |

3.2	In line with advice from the Office of the Deputy Prime Minister (ODPM) where both Minerals and Waste Development Plan Documents (DPD’s) need to be prepared (which is the case in Warwickshire), the MWDS identifies that priority will be given to the Waste DPD. This reflects the need for up-to-date waste plans to support the delivery of the Government’s national waste strategy and the contribution this makes to meeting EU obligations.  The existing Minerals Local Plan still provides land for mineral working, which at recent rates would last for approximately 17 years. Therefore, the priority is on the Waste DPDs and the for the Minerals DPDs will be prepared on a slightly longer timescale.

The Evidence base of the Minerals and Waste Development Framework

3.3	The main sources of data that are relevant to the preparation of the Minerals and Waste Development Documents are as follows: -

Internal to the County Council

- Minerals landbanks and planning permissions

- Landfill capacities and capacities for treatments of waste and waste planning permissions

- Environmental records – designated areas for protection of nature and historic interest

- Transport

- Public rights of way

External

- Water resources, pollution control, contaminated land and waste arisings

- Pollution control

  - Minerals resource mapping

  - Mining hazards

  - Protected species

Sustainability Appraisal

3.4	The County Council must comply with the European Union Directive 2001/42/EC, which requires a strategic environmental assessment of certain plans and programmes. The Directive will apply to all Development Plan Document, and as such a Sustainability Appraisal (SA) will be required to be produced for each.

Annual Monitoring Report

3.5	The Council is required to monitor annually the effectiveness of the policies contained within its LDDs.  For the purposes of this report, the Council will be monitoring the policies of both the Waste and Minerals Development Documents and is required to produce an Annual Monitoring Report (AMR)  The report will be prepared annually and will be published by the County Council on or before 31st December each year.  Guidance indicated that there should be consultation with stakeholders and that the County Council’s report should contribute to the regional monitoring processes.

3.6	This report will assess the following aspects as to the progress of the two plans:-

- Meeting the targets set in Minerals and Waste Development Documents, and the achievement towards the PSA6 targets.

- Assess the impact that the policies are having on other targets set at national, regional and local level,

- Progress in achieving milestones in the preparation of mineral and waste development documents as defined in the Local Development Scheme.

- Identify any policies that need to be considered for early review to meet sustainable development objectives.

- Actions to be taken if policies are to be reviewed.

4	Supporting Statement

Political Management of the Minerals and Waste Development Framework

4.1	Under the previous planning system, responsibility for approving those planning documents that now fall within the scope of this Minerals and Waste Development Scheme was as follows:

The Development Plan (the structure plan and minerals and waste plans) required to be approved by full council following a recommendation from the Council’s Cabinet.  This applied to all key decisions relating to the contents of the plans.

4.2	The new system will require for new arrangements to be put in place to allow effective decision making by the Council.  It is proposed that, subject to the necessary formal amendments being agreed to the County Council’s constitution, approvals of Local Development Documents are made by the following committees.

| Document | To include | To be approved by |
| --- | --- | --- |
| All Development Planning Documents | Core strategies and all other DPDs that are subject to full public examination as required by the Act. | Full Council following a recommendation by Cabinet |
| Statement of Community Involvement |  | Cabinet |
| Local Development Scheme |  | Cabinet |
| Supplementary Planning Documents |  | Cabinet |

Delivering the Minerals and Waste Development Scheme – What could go wrong?

4.3	There will always be a level of uncertainty associated with a document such as this Minerals and Waste Development Scheme.  It is legitimate to ask how reasonable and achievable are the targets set out above, and what issues may affect the overall delivery of the MWDS.

4.4	As part of preparing this MWDS, the County Council has carried out a Risk Assessment of the projects contained in this document, and has identified a number of areas of risk.

- Level of public engagement.  An assumption has been made of the amount of time that will need to be allocated to public and stakeholder involvement.  Whilst this has been based on past experience, it cannot accurately predict how many people will wish to engage with the council on a particular project.

- Capacity of the Planning Inspectorate (PINS).  We have made assumptions on the ability of PINS to service the requirements from this MWDS.  If PINS cannot meet their requirements of this MWDS, then there will be some slippage in the programme. A SLA will be signed with PINS once the MWDS is in effect.

- Changes in government legislation and regulations. This MWDS has been based on the most up-to-date Government guidance.  In view of the legislative changes that are taking place, guidance is currently being drafted, and further guidance , there may be impact upon processes and targets.

- Staff turnover.  There is a degree of flexibility within the MWDS to allow for staff to be re-deployed to meet key targets.

- Additional unforeseen pressures on staff time.  These can never be predicted in advance, however the Council is committed to making available the resources to plug any gaps brought about by such unforeseen pressures.

Contact details

4.5	For more information about any of the issues raised in this Minerals and Waste Development Scheme please contact:-

Strategy Unit

Department of Planning & Economic Strategy

Warwickshire County Council

PO Box 43

Shire Hall

Warwick

CV34 4SX

Tel:  01926 412061

Email:  planningstrategy@warwickshire.gov.uk

This document, together with all other Minerals and Waste Development Documents produced by Warwickshire County Council will be made available on the Council’s web site;  www.warwickshire.gov.uk/planning.

Appendix 1: Schedule of proposed Local Development Documents

| Document Title | Status | Role and content | Geographical coverage | Chain Of Conformity | Consultation On Issues & Options | Consultation On Preferred Options & Proposals | Date For Submission To SoS | Proposed date for adoption |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Statement of community Involvement | Non-Development Plan document | Document outlining community engagement on LDDs and major planning applications | Whole authority area | Must be in conformity with regulations | N/A | July 2005 | November2005 | May 2006 |
| Waste Core Strategy | Development Plan document | Sets out vision, objectives and district spatial development strategy | Whole authority area | Must be in general conformity with RSS. All other LDD’s will be in conformity with core strategy. | February 2006 | August 2006 | January 2007 | February 2008 |
| Waste Allocations DPD | Development Plan document | Will provide detailed allocations for waste related development and criteria based policies where this is not possible. | Whole authority area | Must be in general conformity with Core Strategy. | June 2008 | October 2008 | February 2009 | May 2010 |
| Minerals Core Strategy | Development Plan document | Sets out vision, objectives and district spatial development strategy | Whole authority area | Must be in general conformity with RSS. All other LDD’s will be in conformity with core strategy. | July 2006 | January 2007 | June 2007 | September 2008 |
| Minerals Allocations DPD | Development Plan document | Will provide detailed allocations for mineral related development and criteria based policies where this is not possible. | Whole authority area | Must be in general conformity with Core Strategy. | March 2008 | June 2008 | November 2008 | May 2010 |
| Proposals Map | Development Plan document | A Submission proposals map will accompany the submission of each DPD and will illustrate all the policies set out. (it may be the case that Core Strategies may not necessitate a change to an Adopted Proposals Map) | Whole authority area | N/A | See core strategy | See core strategy | See core strategy | See core strategy |

Appendix 2:  Programme Management of Local Development Documents

| Document Title | F 0 5 | M | A | M | J | J | A | S | O | N | D | J 06 | F | M | A | M | J | J | A | S | O | N | D | J 07 | F | M | A | M | J | J | A | S | O | N | D | J 0 8 | F | M | A | M | J | J | A | S | O | N | D | J 0 9 | F | M |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Saved Waste Local Plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Saved Minerals Local Plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Statement of community involvement |  |  |  |  |  |  |  |  |  | S |  | PM |  | E |  | A |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Waste Core strategy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | S |  |  |  | PM |  |  | E |  |  |  |  |  | A |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Waste Allocation DPD |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | S |  |
| Minerals Core Strategy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | S |  |  |  | PM |  |  | E |  |  |  |  |  |  |  | A |  |  |  |  |  |  |
| Minerals Allocation DPD |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | S |  |  |  |  |

DPD Pre-Production						SCI Pre-Production			S = Submission to SoS	E = Examination

DPD Production							SCI Production				A = Adoption of Plan

DPD Examination							SCI Examination				PM = Pre-examination meeting

Appendix 3:	Profiles of each Local Development Document

#### 1.	Statement of Community Involvement

#### Overview

| ##### Role & Subject | It will set out how the County Council intends to consult with the local community and key stakeholders during the plan making process and in determining planning applications. |
| --- | --- |
| Coverage | County-wide, involving all agencies and organisations with an interest in minerals and waste issues. |
| Status | A Local Development Document, but not a DPD |
| Conformity | Must meet the minimum requirements as set out in the Regulations as well as the Council’s Corporate Consultation Strategy. |

Timetable

| Stage | Dates |
| --- | --- |
| Scoping and early stakeholder and community engagement | February - March 2005 |
| Consultation and participation on draft SCI | July 2005 |
| Date of submission to SoS | November 2005 |
| Pre-examination meeting (if required) | January 2006 |
| Examination | March 2006 |
| Estimated date for adoption | May 2006 |

Arrangements for Production

| #### Organisational Lead | Director of Planning, Transport and Economic Strategy |
| --- | --- |
| #### Political Management | SCI will be approved by Cabinet. |
| #### Internal Resources | Resources from Strategy Unit and Development Group. Administrative support Costs of production, e.g. printing, and postage costs Pre-examination costs. |
| #### Community & Stakeholder Involvement | Wide stakeholder and community involvement with an interest in minerals and waste issues. |
| #### Monitoring and Review | The SCI will be monitored in line with the Council’s Corporate Consultation Strategy. |

2.	Waste Core Strategy

#### Overview

| ##### Role & Subject | The Core Strategy will contain the vision, objectives and strategy for waste development and provide the framework for waste development control. |
| --- | --- |
| Coverage | County-wide, involving all agencies and organisations with an interest in minerals and waste issues. |
| Status | Development Plan Document |
| Conformity | With the RSS |

Timetable

| Stage | Dates |
| --- | --- |
| Early stakeholder and community engagement | June 2005 |
| Consultation date: Issues and options | February 2006 |
| Consultation date: Preferred options and proposals | August 2006 |
| Date of submission to SoS and public consultation on Core Strategy | January 2007 |
| Pre-examination meeting | May 2007 |
| Examination | August 2007 |
| Estimated date for adoption | February 2008 |

Arrangements for Production

| #### Organisational Lead | Director of Planning, Transport and Economic Strategy |
| --- | --- |
| #### Political Management | Core Strategy will be approved by Full Council following a recommendation by Cabinet. |
| #### Internal Resources | Resources from Strategy Unit and Development Group. Administrative support Costs of production, e.g. printing, and postage costs Pre-examination costs. |
| #### Community & Stakeholder Involvement | Wide stakeholder and community involvement with an interest in minerals and waste issues, in accordance with the SCI. |
| #### Monitoring and Review | The Annual Monitoring Report will review actual progress with the targets and milestones as set out in the MWDS, as well as the effectiveness of the DPDs |

3	Waste Allocation DPD

#### Overview

| ##### Role & Subject | Will provide detailed allocations for waste related development and criteria based policies where this is not possible. |
| --- | --- |
| Coverage | County-wide, involving all agencies and organisations with an interest in minerals and waste issues. |
| Status | Development Planning Document |
| Conformity | With the waste Core Strategy |

Timetable

| Stage | Dates |
| --- | --- |
| Early stakeholder and community engagement | March 2008 |
| Consultation date: Issues and options | June 2008 |
| Consultation date: Preferred options and proposals | October 2008 |
| Date of submission to SoS and public consultation on DPD | February 2009 |
| Pre-examination meeting | August 2009 |
| Examination | November 2009 |
| Estimated date for adoption | May 2010 |

Arrangements for Production

| #### Organisational Lead | Director of Planning, Transport and Economic Strategy |
| --- | --- |
| #### Political Management | Waste Allocations DPD will be approved by Full Council following a recommendation by Cabinet. |
| #### Internal Resources | Resources from Strategy Unit and Development Group. Administrative support Costs of production, e.g. printing, and postage costs Pre-examination costs. |
| #### Community & Stakeholder Involvement | Wide stakeholder and community involvement with an interest in minerals and waste issues, in accordance with the SCI. |
| #### Monitoring and Review | The Annual Monitoring Report will review actual progress with the targets and milestones as set out in the MWDS, as well as the effectiveness of the DPDs |

4.	Minerals Core Strategy

#### Overview

| ##### Role & Subject | The Core Strategy will contain the vision, objectives and strategy for minerals development and provide the framework for minerals development control. |
| --- | --- |
| Coverage | County-wide, involving all agencies and organisations with an interest in minerals and waste issues. |
| Status | Development Planning Document |
| Conformity | With the RSS |

Timetable

| Stage | Dates |
| --- | --- |
| Early stakeholder and community engagement | February 2006 |
| Consultation date: Issues and options | July 2006 |
| Consultation date: Preferred options and proposals | January 2007 |
| Date of submission to SoS and public consultation on core strategy | June 2007 |
| Pre-examination meeting | October 2007 |
| Examination | January 2008 |
| Estimated date for adoption | September 2008 |

Arrangements for Production

| #### Organisational Lead | Director of Planning, Transport and Economic Strategy |
| --- | --- |
| #### Political Management | The Minerals Core Strategy will be approved by Full Council following a recommendation by Cabinet. |
| #### Internal Resources | Resources from Strategy Unit and Development Group. Administrative support Costs of production, e.g. printing, and postage costs Pre-examination costs. |
| #### Community & Stakeholder Involvement | Wide stakeholder and community involvement with an interest in minerals and waste issues, in accordance with the SCI. |
| #### Monitoring and Review | The Annual Monitoring Report will review actual progress with the targets and milestones as set out in the MWDS, as well as the effectiveness of the DPDs |

5.	Minerals Allocations DPD

#### Overview

| ##### Role & Subject | Will provide detailed allocations for mineral related development and criteria based policies where this is not possible. |
| --- | --- |
| Coverage | County-wide, involving all agencies and organisations with an interest in minerals and waste issues. |
| Status | Development Planning Document |
| Conformity | With the RSS |

Timetable

| Stage | Dates |
| --- | --- |
| Early stakeholder and community engagement | December 2007 |
| Consultation date: Issues and options | March 2008 |
| Consultation date: Preferred options and proposals | June 2008 |
| Date of submission to SoS | November 2008 |
| Public Consultation on DPD | February 2009 |
| Pre-examination meeting | June 2009 |
| Examination | September 2009 |
| Estimated date for adoption | May 2010 |

Arrangements for Production

| #### Organisational Lead | Director of Planning, Transport and Economic Strategy |
| --- | --- |
| #### Political Management | The Minerals Allocation DPD will be approved by Full Council following a recommendation by Cabinet. |
| #### Internal Resources | Resources from Strategy Unit and Development Group. Administrative support Costs of production, e.g. printing, and postage costs Pre-examination costs. |
| #### Community & Stakeholder Involvement | Wide stakeholder and community involvement with an interest in minerals and waste issues, in accordance with the SCI. |
| #### Monitoring and review | The Annual Monitoring Report will review actual progress with the targets and milestones as set out in the MWDS, as well as the effectiveness of the DPDs |

6.	Proposals Map

#### Overview

| ##### Role & Subject | A Submission proposals map will accompany the submission of each DPD and will illustrate all the policies set out. (it may be the case that Core Strategies may not necessitate a change to an Adopted Proposals Map). The County Council will work with the District Councils, who must include on their adopted proposals map, safeguarded areas, mineral consultation areas and any adopted minerals and waste allocations. |
| --- | --- |
| Coverage | County-wide |
| Status | Development Plan Document |
| Conformity | N/A, however, will need to conform will all adopted DPDs. |

Timetable

The submission proposals map will be prepared alongside the DPDs. The proposals map will be revised every time a DPD is revised. Therefore, the timetable for preparation will be the same as these.

Arrangements for Production

| #### Organisational Lead | See ‘Core Strategy’ |
| --- | --- |
| #### Political Management | See ‘Core Strategy’ |
| #### Internal Resources | See ‘Core Strategy’ |
| #### Community & Stakeholder Involvement | See ‘Core Strategy’ |
| #### Monitoring and Review | See ‘Core Strategy’ |

Appendix 4: Relationship between the Local Development Documents and other Development Plan Documents

Warwickshire Minerals Local Plan

Regional Spatial Strategy

Warwickshire Structure Plan “saved” until Sept 2007

Warwickshire Waste Local Plan

Core Strategy

Core Strategy

Key

“Saved” plans

prepared by WCC

LDDs prepared

by WCC

RSS prepared by

RPB

Chain of conformity

for DPD’s

Chain of conformity

for Non DPD’s

Proposals Map

Allocations DPD

Allocations DPD

Proposals Map

Statement of Community Involvement

Appendix 5: Schedule of Replacement of Minerals and Waste Local Plan ‘Saved’ Policies

Minerals Local Plan for Warwickshire (1995)

| Chapter | Policy | To be replaced by |
| --- | --- | --- |
| 4. Selection of Potential Sites | M1 | Allocations DPD |
| 5. Investigation and Exploration | M2 | Core Strategy |
|  | M3 | Core Strategy |
| 6. Development Control | M4 | Core Strategy |
|  | M5 | Core Strategy |
|  | M6 | Core Strategy |
|  | M7 | Core Strategy |
| 7. Restoration and Aftercare | M9 | Core Strategy |
|  | M10 | Core Strategy |

The Waste Local Plan for Warwickshire (1999)

| Chapter | Policy | To be replaced by |
| --- | --- | --- |
| 3. Policies & Proposals | No. 1 General land use | Core Strategy |
|  | No. 2 Conditions and Agreements | Core Strategy |
|  | No. 3 Landfilling | Core Strategy |
|  | No 4 Land-Raising | Core Strategy |
|  | No 5 Incinerators | Core Strategy |
|  | No 6 Material Recycling Facilities | Core Strategy |
|  | No 7 Scrap Yards | Core Strategy |
|  | No 8 Transfer Stations | Core Strategy |
|  | No 9 Large Scale Composting | Core Strategy |
|  | No 10 Household Waste Facilities | Core Strategy |
|  | No 11 Other Development | Core Strategy |
|  | No 12 Segregation of Waste Streams | Core Strategy |
|  | No 13 Proposed Facilities | Allocations DPD |
|  | No 14 Jees and Boons Quarry & Midland Quarry | Allocations DPD |

The Minerals and Waste Local Plans will be ‘saved’ for three years, and will be progressively replaced by DPDs within the MWDF. If necessary a case will be made in subsequent MWDS to save certain policies beyond September 2007.