## Sheet1
Main Train Programme
TARGET DATE | STATUS | DISTRICT | REF # | ROAD NO. | PARISH | ROAD | FROM | TO
2022-04-05 | Not Started | North Warks | AH106 | B4098 | Corley | Tamworth Road | M6 bridge | Coventry boundary
2022-04-05 | Not Started | Nun & Bed | AH206 | D1432 | Nuneaton | Crowhill Road | Eastboro Way | Lutterworth Road
2022-04-06 | Not Started | Stratford | AH501 | C208 | Ullenhall | Ullenhall Lane | Oldberrow Hill Farm | County Boundary
2022-04-06 | Not Started | Stratford | AH502 | C208 | Ullenhall | Grimshaw Hill/Henley Road | A4189 New Road | 30mph Entering Ullenhall Village
2022-04-06 | Not Started | Stratford | AH500 | D5257 | Claverdon | Kington Lane | Henley Road | Langley Road
2022-04-07 | Not Started | Stratford | AH510 | C47 | Dorsington | Dorsington Road | Mickleton Road | Surface change
2022-04-07 | Not Started | Stratford | AH527 | C47 | Quinton | Main Street | St Swithen's Drive | Villlage Boundary
2022-04-07 | Not Started | Warwick | AH426 | C209 | Barford | Barford Road | S/C at "Four Winds" | S/C by A452 overbridge (2021 SD joint)
2022-04-07 | Not Started | Warwick | AH442 | D6017 | Bishop's Tachbrook | Mallory Road | Severn Acre Close | Banbury Road
2022-04-08 | Not Started | Warwick | AH404 | D2220 | Kenilworth | Dalehouse Lane (1) | Lulworth Park | 50mph limit
2022-04-08 | Not Started | Warwick | AH405 | D2220 | Kenilworth | Dalehouse Lane (2) | 50mph limit | Dalehouse Farm entrance
2022-04-08 | Not Started | Stratford | AH515 | C36 | Southam | Welsh Rd West | Junc Coventry Rd | Junc Bascote Rd
2022-04-08 | Not Started | Stratford | AH517 | C97 | Bascote Heath | Bascote Rd | Welsh rd | A425
2022-04-09 | Not Started | Rugby | AH307 | A4071 | Rugby | Blue Boar | Back of splitter with Rugby Road | Back of splitter with Straight Mile
2022-04-09 | Not Started | Rugby | AH309 | B4642 | Rugby | Bilton Road | Lytham Road | Buchanan Road
2022-04-09 | Not Started | Warwick | AH400 | A4177 | Hatton | Birmingham Road | Brownley Green Lane | S/C at entrance to Home Farm
2022-04-09 | Not Started | Warwick | AH402 | B4439 | Lapworth | Old Warwick Road | Entrance to The Old Barn | Wharf Lane
2022-04-09 | Not Started | Warwick | AH401 | B4439 | Shrewley Common | Hockley Road | Five Ways Road | S/C just beyond Mill Lane
2022-04-09 | Not Started | Warwick | AH412 | A425 | Radford Semele | Southam Road | S/C at 30mph signs | S/C just before Offchurch Lane
2022-04-10 | Not Started | Warwick | AH441 | A452 | Bishop's Tachbrook | Banbury Road | M40 Off Slip Road | Greys Mallory island
2022-04-10 | Not Started | Stratford | AH525 | A439 | Black Hill | A439 Warwick Road | A46 Stratford Bypass | X-Roads by Mercedes Garage
2022-04-10 | Not Started | Nun & Bed | AH208 | B4113 | Exhall | Coventry Road | Black Bank | Hayes Lane
2022-04-10 | Not Started | Rugby | AH305 | A426 | Brownsover | Leicester Road | Central Park Island | Newton Manor Lane Island
2022-04-11 | Not Started | North Warks | AH104 | D389 | Curdworth | Marsh Lane | S/C near Hams Hall Island | Traffic Calming near Village
2022-04-11 | Not Started | North Warks | AH102 | C5 | Polesworth | High Street | The Spread Eagle Pub | No 75
2022-04-11 | Not Started | North Warks | AH103 | C120 | Atherstone | Sheepy Road | Block paving near A5 bridge | County boundary with Leicestershire
2022-04-11 | Not Started | Nun & Bed | AH207 | D1498 | Bedworth | Marston Lane | Canal Bridge | Leicester Road
2022-04-12 | Not Started | Rugby | AH302 | C206 | Wolvey | Mere Lane | Copston Fields Farm | Fosse Way (Cloudesley Bush)
2022-04-12 | Not Started | Rugby | AH303 | D3061 | Brownsover | Newton Manor Lane | Crowthorns | St Thomas Cross junction
2022-04-12 | Not Started | Warwick | AH413 | C91 | Radford Semele | Offchurch Lane | Village speed limit signs adj 42/44 | S/C just before Radford Lane
2022-04-12 | Not Started | Warwick | AH429 | D4245 | Warwick | Wedgnock Lane | Canal bridge | S/C at culvert
2022-04-12 | Not Started | Warwick | AH403 | A452 | Kenilworth | Leamington Road | S/C o/s 76 | S/C at start of gyratory
2022-04-13 | Not Started | Stratford | AH528 | A3400 | Atherstone on Stour | Shipston Road | Monks Barn Farm | Junction with Preston Lane
2022-04-13 | Not Started | Stratford | AH506 | B4088 | Salford Priors | B4088 Salford Road | Worc's County boundary | School Road at Iron Cross
2022-04-13 | Not Started | Stratford | AH507 | B4088 | Salford Priors | B4088 Salford Road | School Road at Iron Cross | Broom Lane at Dunnington
2022-04-14 | Not Started | Stratford | AH526 | A422 | Ettington/Pillerton | A422 Banbury Road | Hays Meadow | Halford Road
2022-04-19 | Not Started | Stratford | AH518 | A429 | Halford | A429 Fosse Way | South of village from newly resurfaced section | A3400/A429 traffic Island by Subaru Garage
2022-04-19 | Not Started | Stratford | AH520 | A3400 | Newbold on Stour | Shipston Road | Crimscote Road | Mill Lane
2022-04-19 | Not Started | Stratford | AH516 | B4087 | Ashorne | Newbold Rd | Crematoria | just north of Newbold pacey
2022-04-20 | Not Started | Rugby | AH300 | B4029 | Brinklow | Ansty Road | S/C near Walkers Terrace | S/C near Junc. Peter Hall Lane
ON HOLD DUE TO PERMITS | Not Started | Warwick |  | A452 | Kenilworth | Thickthorn island | Splitter | Splitter
Combi Programme
TARGET DATE | STATUS | DISTRICT | REF # | ROAD NO. | PARISH | ROAD | FROM | TO
2022-07-11 | Not Started | Nun & Bed | AH200 | D1024 | Nuneaton | Hillside Drive | Berrington Road | End
2022-07-11 | Not Started | Nun & Bed | AH201 | D1022 | Nuneaton | Cleveley Drive | Berrington Road | Arlon Avenue
2022-07-11 | Not Started | Nun & Bed | AH202 | D1021 | Nuneaton | Berrington Road | Mancetter Road | Camp Hill Road
2022-07-11 | Not Started | Nun & Bed | AH203 | D1023 | Nuneaton | Arlon Avenue | Berrington Road | Camp Hill Road
2022-07-11 | Not Started | Nun & Bed | AH204 | D1437 | Nuneaton | Wentworth Drive | Golf Drive | End
2022-07-12 | Not Started | Warwick | AH406 | D7401 | Kenilworth | Turton Way | Dencer Drive | End of road
2022-07-12 | Not Started | Warwick | AH407 | D7402 | Kenilworth | Courthouse Croft | Turton Way | End of road
2022-07-12 | Not Started | Warwick | AH408 | D7385 | Kenilworth | Allitt Grove | Villiers Road | End of road
2022-07-12 | Not Started | Warwick | AH409 | D7026 | Kenilworth | Convent Close | Coventry Road | End of road
2022-07-12 | Not Started | Warwick | AH411 | D7015 | Kenilworth | Castle Hill | Castle Road | s/c 30m after Malthouse Lane jnc
2022-07-12 | Not Started | Warwick | AH415 | C32 | Bubbenhall | Bubbenhall Road | Coventry Road | S/C by track to sewage works
2022-07-13 | Not Started | Warwick | AH416 | D4549 | Cubbington | Ladycroft | Offchurch Road | End of road & up to 4 Brookfield Road
2022-07-13 | Not Started | Warwick | AH417 | D4550 | Cubbington | Price Road | Offchurch Road | New Street
2022-07-13 | Not Started | Warwick | AH418 | D4476 | Lillington | Elan Close | Valley Road | End of road
2022-07-13 | Not Started | Warwick | AH419 | D4471 | Lillington | Severn Close | Valley Road | End of road
2022-07-13 | Not Started | Warwick | AH420 | D4478 | Lillington | Wye Close | Valley Road | End of road
2022-07-13 | Not Started | Warwick | AH421 | D4483 | Lillington | Charnwood Way | Parklands Avenue | End of road
2022-07-13 | Not Started | Warwick | AH422 | D4485 | Lillington | Exmoor Drive | Parklands Avenue | End of road
2022-07-13 | Not Started | Warwick | AH423 | D4487 | Lillington | Sherwood Walk | Parklands Avenue | End of road
2022-07-13 | Not Started | Warwick | AH424 | D4487 | Lillington | Vicarage Road | Cubbington Road | Church Lane
2022-07-14 | Not Started | Warwick | AH425 | A425 | Leamington Spa | Park Drive | Princes Drive | Park / tennis courts entrance
2022-07-14 | Not Started | Warwick | AH436 | D4301 | Leamington Spa | Wheathill Close | Beverley Road | End of road
2022-07-14 | Not Started | Warwick | AH428 | D4336 | Leamington Spa | Milverton Hill / Portland Place West | Church Hill | Dale Street / Adelaide Road
2022-07-14 | Not Started | Warwick | AH414 | D2351 | Offchurch | Radford Lane / Village Street | Offchurch Lane | School Hill
2022-07-14 | Not Started | Stratford | AH514 | D2339 | Long Itchington | Church Rd | C33 Leamington Rd | D2338 Short Lane
2022-07-14 | Not Started | Warwick | AH433 | D4973 | Warwick | Hind Close | Kirby Avenue | End of road
2022-07-14 | Not Started | Warwick | AH434 | D4983 | Warwick | Yardley Close | Woodloes Avenue North | End of road
2022-07-14 | Not Started | Warwick | AH435 | D4986 | Warwick | Corbinson Close | Deansway | End of road
2022-07-15 | Not Started | Warwick | AH437 | D4079 | Warwick | Malham Road | Woodloes Avenue South | Langcliffe Avenue
2022-07-15 | Not Started | Warwick | AH438 | D4077 | Warwick | Langcliffe Avenue | no1 | no79
2022-07-15 | Not Started | Warwick | AH439 | D4994 | Warwick | Leyburn Close | Lagcliffe Avenue | End of road
2022-07-15 | Not Started | Warwick | AH440 | D4078 | Warwick | Thornton Close | Lagcliffe Avenue | End of road
2022-07-15 | Not Started | Stratford | AH521 | D6600 | Shipston | Warwick Place | Darlingscote Road | End of cul-de-sac
2022-07-15 | Not Started | Stratford | AH522 | D6602 | Shipston | Berry Avenue | Darlingscote Road | Queens Avenue
2022-07-15 | Not Started | Stratford | AH523 | D6598 | Shipston | Pittway Avenue | End | End
2022-07-15 | Not Started | Stratford | AH504 | D6122 | Stratford | Slingates Road | Jolyffe Park Road | St Mary's Road
2022-07-15 | Not Started | Stratford | AH505 | D6123 | Stratford | Talbot Road | Jolyffe Park Road | Slingates Road
2022-07-15 | Not Started | Stratford | AH512 | D5265 | Bidford-on-Avon | Saxonfields | High Street | The Bank
2022-07-16 | Not Started | Warwick | AH410 | C93 | Hatton Green | The Green | Birmingham Road | Hockley Road
2022-07-16 | Not Started | Warwick | AH427 | B4087 | Bishops Tachbrook | Oakley Wood Road | Banbury Road | Start of railings on M40 overbridge
2022-07-16 | Not Started | Stratford | AH503 | D5234 | Kite Green | Edge Lane | A4189 Whitley Hill | Stratfrord/Warwick Boundary
2022-07-16 | Not Started | Stratford | AH529 | E6329 | Wellesbourne | Hunscote Lane | Lower Hunscote Farm | Wayside cottage
2022-07-17 | Not Started | Warwick | AH442 | D6017 | Bishop's Tachbrook | Mallory Road | Severn Acre Close | Banbury Road
2022-07-17 | Not Started | Warwick | AH432 | D4258 | Warwick | Nelson Lane | Coventry Road | Wharf Street
2022-07-17 | Not Started | Warwick | AH431 | D4136 | Warwick | Montague Road | Charles Street | Spinney Hill
2022-07-17 | Not Started | Stratford | AH530 | E6476 | Oxhill | Oxhill Bridle way | School Cottages | End of road