## Sheet1
Main Train Programme
TARGET DATE | STATUS | REF # | ROAD NO. | PARISH | ROAD NAME | FROM | TO
2023-05-02 | Complete | SD34 | B5439 | No Mans Heath | Ashby Road | County Boundary | National speed limit change
2023-05-02 | Complete | SD54 | C7 | Polesworth | Station Road | Nethersole Street | Pooley View
2023-05-02 | Complete | SD36 | B5000 | Grendon | Grendon Road | Before Canal bridge | Junction Spon Lane
2023-05-02 | Complete | SD63 | C7 | Hurely | Hurey common | Football club car park | SURFACE CHANGE ANTISKID
2023-05-02 | Complete | SD35 | B4098 | Nether Whitacre | Tamworth Road | Before junction Ridley Lane | s/c near Botts Green Lane
2023-05-02 | Complete | SD55 | C125 | Kingsbury | Coton Road/Bodymoor Heath Road | Marston Island Splitter | Dog Lane
2023-05-03 | Complete | SD42 | B4114 | Wolvey | Smockington Lane | Lutterworth Road | Copston Lodge Farm
2023-05-03 | Complete | SD40 | C206 | Wolvey | Gipsy Lane | Hinckley Road | Lutterworth Road
2023-05-03 | Complete | SD41 | C206 | Wolvey | Cloudesley Bush Lane/Mere Lane | Lutterworth Road | Copston Fields Farm
2023-05-03 | Complete | SD50 | D1670 | Bedworth | Woodland Lane (linked with SD51) | Charles Eaton Road (North) | Bedworth Lane
2023-05-03 | Complete | SD51 | D1670 | Bedworth | Bedworth Lane (linked with SD50) | Woodlands Lane | Astley Lane
2023-05-04 | Complete | SD47 | D1824 | Keresley | Exhall Road | Bennetts Road | New Road
2023-05-04 | Complete | SD37 | C64 | Corley | Smorrall Lane | Highfield Lane | Hospital Lane
2023-05-04 | Complete | SD57 | B4112 | Withybrook | Withybrook Road | 5 ways cross roads | Bow Lane
2023-05-04 | Complete | SD56 | C168 | Burton Hastings | Burton Lane | Hinckley Road | Lutterworth Road
2023-05-05 | Complete | SD38 | D1469 | Nuneaton | Milby Drive | Woodcote Avenue | Pallett Drive
2023-05-05 | Complete | SD46 | A428 | Brandon | Rugby Road | Surface change outside of Ivy House Farm | Speedway Lane junction
2023-05-05 | Complete | SD62 | A428 | Brandon/Bretford | Brandon Road | Avondale Road | Queens Road
2023-05-05 | Complete | SD9 | C39 | Norton Lindsey | Littleworth Lane (Warwick Road) | Watery Lane | Brittons Lane
2023-05-09 | Complete | SD32 | C33 | Long Itchington | Leamington Rd | 30/50 signs on village exit | Hunningham
2023-05-09 | Complete | SD61 | C174 | Hill/Leamington Hastings | Birdingbury Road/Leamington Hastings Road | A426 Southam Road | S/C (new surfacing) prior to Birdingbury
2023-05-09 | Complete | SD17 | B4463 | Budbrooke | Watery Lane | A46 island | Sherbourne Farm access road
2023-05-10 |  | SD30 | A425 | Napton | Daventry Rd | Canal Bridge on West side of Napton | Shuckbrugh
2023-05-10 |  | SD31 | B4451 | Southam | Gaydon Rd | Plough Lane | Junction Knighcote Bottoms
2023-05-11 | Complete | SD29 | B4035 | Shipston | Mill Lane | A3400 Gyratory | Fell Mill Lane x-road
2023-05-11 | Complete | SD27 | A429 | Ettington/Halford | Halford Road | Ettington Island | Halford Island
2023-05-11 | Complete | SD22 | C104 | Clifford Chambers | Milcote Road linked to SD23 | Campden Road | Preston Fields Lane
2023-05-12 | Complete | SD23 | C104 | Clifford Chambers | Milcote Road linked to SD22 | Preston Fields Lane | Long Marston Road
2023-05-12 | Complete | SD20 | C104 | Welford-on-Avon | Barton Road linked to SD21 | Long Marston Road | Bottom of Cress Hill
2023-05-12 | Complete | SD28 | B4632 | Quinton | Campden Road | Taylors Lane Island | County Boundary
2023-05-14 | Complete | SD45 | B4429 | Dunchurch | Daventry Road | Start of dual c/way | M45 island
2023-05-14 | Complete | SD59 | A426 | Rugby | Leicester Road | Tesco roundabout | Avon Mill roundabout (South bound section)
2023-05-14 | Complete | SD60 | A4071 | Rugby | Newbold Road | Avon Mill roundabout | Relief Road roundabout
2023-05-14 | Complete | SD33 | A38 | Middleton | A38 Sutton Coldfield Bypass (N/B) | M6 Toll S/B exit Island | Bassetts Pole Island
2023-05-15 |  | SD4 | A445 | Leam Spa | Lillington Avenue | Binswood Island | Kenilworth Road
2023-05-15 | Complete | SD25 | C40 | Snitterfield | Wolverton Road | School Road | Wolverton
2023-05-15 | Complete | SD26 | B4102 | Earlswood | Earlswood Common | Valley Road | Broad Lane
2023-05-16 | Complete | SD24 | B401 | Tanworth | Broad Lane linked to SD26 | Blind Lane | Tithe Barn Lane
2023-05-16 | Complete | SD1 | A4141 | Wroxall | Birmingham Road | Five Ways Island | Rising Lane
Combi Programme
TARGET DATE | STATUS | REF # | ROAD NO. | PARISH | ROAD NAME | FROM | TO
2023-07-17 |  | SD64 | C78 | Middleton | Church lane | The green man pub | Crowberry lane
2023-07-17 |  | SD66 | D154 | Nuneaton | Watling street (service road) | Service road | End
2023-07-17 |  | SD67 | D1188 | Nuneaton | Beaumont Rd | Vernone lane | Manor court road
2023-07-17 |  | SD52 | D1120 | Nuneaton | Barpool Road | Tomkinson Road | Vernons Lane
2023-07-17 |  | SD39 | D1221 | Nuneaton | Merevale Avenue | Richmond Road | Queens Road
2023-07-18 |  | SD44 | D3209 | Rugby | Railway Terrace | Clifton Road | Wood Street
2023-07-18 |  | SD53 | D1052 | Nuneaton | Cedar Road (Phase 1) | Queen Elizabeth Road | Copper Beech Road
2023-07-19 |  | SD49 | D1559 | Bedworth | Pine Tree Road | Regent Street | Beechwood Road
2023-07-19 |  | SD48 | D1805 | Keresley | Somers Road | Hill Road | End
2023-07-19 |  | SD58 | D2078 | Brinklow | Ell Lane | Brinklow Road | Lutterworth Road
2023-07-19 |  | SD43 | D3059 | Rugby | Brownsover Lane | Lower Lodge Avenue | Brownsover Road
2023-07-20 |  | SD2 | D5066 | Shrewley | Case Lane | Fletchers Lane | Five Ways Road
2023-07-20 |  | SD3 | D7171 | Kenilworth | Raglan Grove | Ilam Park | End of cul-de-sac
2023-07-20 |  | SD5 | D2219 | Stoneleigh | Walkers Orchard | Viacarage Road | End of cul-de-sac
2023-07-20 |  | SD6 | D4903 | Cubbington | Willow Sheets Meadow | Coventry Road | End of cul-de-sac
2023-07-20 |  | SD14 | D4473 | Lillington | Kempton Crescent | Valley Road | End of cul-de-sac
2023-07-20 |  | SD15 | D4482 | Lillington | Ascot Ride | Valley Road | End of cul-de-sac
2023-07-20 |  | SD16 | D4460 | Lillington | Valley Road cul-de-sac | Valley Road | End of cul-de-sac
2023-07-20 |  | SD13 | D4580 | Leamington Spa | Northcote Street | Willes Road | Beaconsfield Street
2023-07-20 |  | SD7 | D4876 | Radford Semele | Valley Road cul-de-sac linked to SD8 | The Valley | Williams Road
2023-07-20 |  | SD8 | D4871 | Radford Semele | Williams Road linked to SD7 | Valley Road | End of cul-de-sac
2023-07-21 |  | SD12 | D5034 | Lapworth | Bakers Lane | Canal bridge at Chapel Lane | Culvert adjacent 17 Bakers Lane
2023-07-21 |  | SD11 | C15 | Burton Green | Red Lane | Burrow Hill Lane | o/s "Thuris"
2023-07-22 |  | SD18 | D4251 | Warwick | Rock Mill Lane | Rugby Road | End of road
2023-07-22 |  | SD10 | D3920 | Warwick Gates | Othello Avenue | Heathcote Lane | Tachbrook road