## Sheet1
Combi Programme 2025/26
S/D TARGET DATE | STATUS | KEILY LOCK DATE | STATUS | REF # | ROAD NO. | PARISH | ROAD NAME | FROM | TO
2025-04-07 | COMPLETED | 2025-04-14 | COMPLETED | 25NW07 | C187 | Hurley | Foul End Lane | Knowle Hill | Just past Dexter Ln
2025-04-07 | COMPLETED | 2025-04-14 | COMPLETED | 25NW22 | D454 | Shustoke | The Green | Church Road | Church Road
2025-04-08 | COMPLETED | 2025-04-14 | COMPLETED | 25NW05 | D391 | Curdworth | Glenfields | Glebe Fields | Entire
2025-04-08 | COMPLETED | 2025-04-16 | COMPLETED | 25NW09 | D319 | Kingsbury | Bromage Avenue | Tame Bank | End of Road
2025-04-08 | COMPLETED | 2025-04-15 | COMPLETED | 25NW11 | D667 | Kingsbury | Hazelcroft | Aspens | End of Road
2025-04-08 | COMPLETED | 2025-04-15 | COMPLETED | 25NW13 | D665 | Kingsbury | The Hawthorns | Fircroft | End
2025-04-08 | COMPLETED | 2025-04-15 | COMPLETED | 25NW19 | D370 | Middleton | Brick Kiln Lane | Jnc Tamworth road | Jnc Wishaw Lane
2025-04-08 | COMPLETED | 2025-04-15 | COMPLETED | 25NW20 | D394 | Curdworth | Oaklands / Glebefields | Coleshill Road | Entire
2025-04-08 | COMPLETED | N/A |  | Remedial site |  | Curdworth | Marsh Lane | Hams Hall Island | Start of Traffic Calming
2025-04-09 | COMPLETED | 2025-04-15 | COMPLETED | 25NW15 | D666 | Kingsbury | The Aspens | Sorrell Drive | End of Road
2025-04-09 | COMPLETED | N/A |  | Remedial site |  | Kingsbury | Coventry Road | Mill Crescent | End of Road
2025-04-10 | COMPLETED | 2025-04-16 | COMPLETED | 25NW10 | D795 | Kingsbury | Redwood Drive | Sorrel Drive | End
2025-04-10 | COMPLETED | 2025-04-16 | COMPLETED | 25NW12 | D324 | Kingsbury | Brook Close | Fircroft | End
2025-04-10 | COMPLETED | 2025-04-16 | COMPLETED | 25NW14 | D663 | Kingsbury | Aldersgate | Sycamore road | End
2025-04-10 | COMPLETED | 2025-04-15 | COMPLETED | 25NW16 | D223 | Kingsbury | Beech Close | Sycamore Road | To End
2025-04-10 | COMPLETED | 2025-04-15 | COMPLETED | 25NW17 | D664 | Kingsbury | Fircroft | Sycamore Road | All
2025-04-10 | COMPLETED | 2025-04-15 | COMPLETED | 25NW27 | D227 | Kingsbury | ROWAN CLOSE | Sycamore Road | End
2025-04-10 | COMPLETED | 2025-04-16 | COMPLETED | 25NW28 | D591 | Kingsbury | CEDAR CRESCENT | Pear tree Avenue | End
2025-04-10 | COMPLETED | 2025-04-16 | COMPLETED | 25NW29 | D225 | Kingsbury | MEADOW CLOSE | Mill Crescent | End
2025-04-10 | COMPLETED | 2025-04-16 | COMPLETED | 25NW30 | D325 | Kingsbury | RANGE WAY | Jnc of Trinity Road
2025-04-11 | COMPLETED | 2025-04-29 | PLANNED | Remedial site |  | Warwick | St Nichols Church street | Smith Street | Castle Hill
2025-04-11 | COMPLETED | 2025-04-16 | COMPLETED | 25NW21 | D62 | Polesworth | St Helena Road | B5000 Grendon Road | Dordon Hall Ln
2025-04-11 | COMPLETED | 2025-04-16 | COMPLETED | 25NW24 | D356 | Wood end | Glenville Avenue | Wood Street | End of Road
2025-04-11 | COMPLETED | 2025-04-28 | COMPLETED | 25NW25 | D194 | Atherstone | BATH ROAD | Margaret Road | End
2025-04-11 | COMPLETED | 2025-04-17 | COMPLETED | 25NW32 | D621 | Atherstone | RIVER DRIVE | Sheepy Road | All
2025-04-11 | COMPLETED | 2025-04-17 | COMPLETED | 25NB04 | D1477 | Nuneaton | Woodcote Avenue | Milby Drive | Pallett Drive
2025-04-11 | COMPLETED | 2025-04-17 | COMPLETED | 25NB05 | D1329 | Nuneaton | Bladen Close | Woodcote Avenue | End
2025-04-12 | COMPLETED | 2025-04-28 | COMPLETED | 25RU17 | D36200 | Dunchurch | Halfway lane | Junction of Lutterworth Road
2025-04-12 | COMPLETED | 2025-04-28 | COMPLETED | 25RU01 | D3338 | Bilton | Edyvean Close | Golf Drive | To End
2025-04-12 | COMPLETED | 2025-04-28 | COMPLETED | 25RU09 | D3478 | Overslade | DEEPMORE ROAD | Armson Road | Armson Road
2025-04-12 | COMPLETED | 2025-04-28 | COMPLETED | 25RU10 | D3481 | Overslade | CHERRY GROVE | Cunningham Way | Entire
2025-04-12 | COMPLETED | 2025-04-28 | COMPLETED | 25RU11 | D3480 | Overslade | LABURBNHAM GROVE | Montgomery Drive | End
2025-04-12 | COMPLETED | 2025-04-28 | COMPLETED | 25RU12 | D2196 | Princethorpe | HIGHTOWN | Nelson Way | End
2025-04-12 | COMPLETED | 2025-04-29 | COMPLETED | 25WA05 | D7361 | Kenilworth | Mountbatten Avenue | Monks Road | (Pinewood Road) Monks Road
2025-04-12 | COMPLETED | 2025-04-29 | COMPLETED | 25WA06 | D7163 | Kenilworth | Knightlow Close | Steele Street | End
2025-04-13 | COMPLETED | 2025-04-29 | COMPLETED | 25WA07 | D7131 | Kenilworth | The Mews | Coombe Drive | End
2025-04-13 | COMPLETED | 2025-04-29 | COMPLETED | 25WA10 | D7134 | Kenilworth | Percy Crescent | Oliver Street | End
2025-04-13 | COMPLETED | 2025-04-29 | COMPLETED | 25WA22 | D7129 | Kenilworth | Caesar Road | Clifton Road | Wood Street
2025-04-13 | COMPLETED | 2025-04-29 | COMPLETED | 25WA23 | D7128 | Kenilworth | Archer Road | Nelson Way | Entire
2025-04-13 | COMPLETED | 2025-04-29 | COMPLETED | 25WA24 | D7126 | Kenilworth | Willoughby Avenue | Coventry Road | End
2025-04-13 | COMPLETED | 2025-04-29 | COMPLETED | 25WA27 | D7127 | Kenilworth | Avon Road | Bawnmore Road | ALL
2025-04-13 | COMPLETED | 2025-04-29 | COMPLETED | 25WA09 | D7159 | Kenilworth | Latimer Close | Overslade lane | Epsom Road
2025-04-13 | COMPLETED | 2025-04-29 | COMPLETED | 25WA21 | D7156 | Kenilworth | Beauchamp Road | Deepmore Road | End
2025-04-13 | COMPLETED | 2025-04-29 | COMPLETED | 25WA26 | D7133 | Kenilworth | Percy Road | Deepmore Road | End
2025-04-14 | COMPLETED | N/A |  | Remedial site |  | Nuneaton | Crowhill Road | B4455 Fosse Way | End
2025-04-14 | COMPLETED | N/A |  | Remedial site |  | Nuneaton | Wentworth Drive ( various sections ) | Heyville Croft | End of road
2025-04-14 | COMPLETED | 2025-04-30 | RE - PROGRAMMED | 25NB01 | D1749 | Exhall | Marshall Road | Mountbatten Avenue | end of road
2025-04-14 | COMPLETED | 2025-04-30 | RE - PROGRAMMED | 25RU06 | D2093 | Binley Woods | SIR WINSTON CHURCHILL PLACE | Ceasar Road | end of road
2025-04-14 | COMPLETED | 2025-04-30 | RE - PROGRAMMED | 25RU08 | D2522 | Binley Woods | ASHDALE CLOSE | John Ogaunt Road | Percy Road
2025-04-14 | COMPLETED | 2025-04-30 | RE - PROGRAMMED | 25RU19 | D3344 | New Bilton | Parnell Close | Fishponds Road | Percy Road
2025-04-14 | COMPLETED | N/A |  | Remedial site |  | Rugby | Railway Terrace ( various sections) | Caesar Road | Archer Road
2025-04-15 | COMPLETED | 2025-04-30 | RE - PROGRAMMED | 25RU03 | D3568 | Bilton | Blake close | Caesar road | Sidderley Avenue
2025-04-15 | COMPLETED | 2025-04-30 | RE - PROGRAMMED | 25RU04 | D3587 | Bilton | PIPEWELL CLOSE | Willoughby Avenue | End
2025-04-15 | COMPLETED | 2025-04-30 | RE - PROGRAMMED | 25RU05 | D3576 | Bilton | DITTON CLOSE | Dudley Road West | Dudley Road
2025-04-15 | COMPLETED | 2025-04-30 | RE - PROGRAMMED | 25RU07 | D3540 | New Bilton | DRYDEN PLACE | Oaks road | Dudley road
2025-04-15 | COMPLETED | 2025-04-30 | RE - PROGRAMMED | 25RU02 | D3588 | Bilton | Queensferry close | John Ogaunt Road | Scott Road
2025-04-15 | COMPLETED | 2025-05-01 | RE - PROGRAMMED | 25WA11 | D7135 | Kenilworth | John Ogaunt Road | Oaks Road | End of Road
2025-04-15 | COMPLETED | 2025-04-29 | COMPLETED | 25WA14 | D7151 | Kenilworth | Guy Road | John Ogaunt Road | Siddeley Avenue
2025-04-15 | COMPLETED | 2025-05-01 | RE - PROGRAMMED | 25WA60 | D7164 | Kenilworth | LINDSEY CRESCENT | Mortimer Road | Roseland Road
2025-04-16 | COMPLETED | 2025-05-01 | RE - PROGRAMMED | 25WA12 | D7122 | Kenilworth | Fishponds Road | Suncliffe Drive | Suncliffe Drive
2025-04-16 | COMPLETED | 2025-05-01 | RE - PROGRAMMED | 25WA13 | D7101 | Kenilworth | Thickthorne Close / Thickthorne Orchards | Birches Lane | End
2025-04-16 | COMPLETED | 2025-05-01 | RE - PROGRAMMED | 25WA56 | D7070 | Kenilworth | NEWFIELD AVENUE | Lindisfarne Drive | End
2025-04-16 | COMPLETED | 2025-05-01 | RE - PROGRAMMED | 25WA64 | D7175 | Kenilworth | HARGER COURT / HARGER MEWS | Lindisfarne Drive | End
2025-04-17 | COMPLETED | 2025-05-02 | RE - PROGRAMMED | 25WA41 | D4260 | Leamington Spa | Blandford Road | Lindisfarne Drive | Casita Grove
2025-04-17 | COMPLETED | 2025-05-02 | RE - PROGRAMMED | 25WA42 | D4917 | Leamington Spa | Stephenson Close | Inverary Close | End of Road
2025-04-17 | COMPLETED | 2025-05-02 | RE - PROGRAMMED | 25WA43 | D4254 | Leamington Spa | Albert Street | Windy Arbour | End of Road
2025-04-17 | COMPLETED | 2025-05-02 | RE - PROGRAMMED | 25WA44 | D4253 | Leamington Spa | Edward Street | Windy Arbour | Kineton Road
2025-04-17 | COMPLETED | 2025-05-02 | RE - PROGRAMMED | 25WA45 | D4920 | Leamington Spa | St Albans Close | Warwick Road | End
2025-04-22 | COMPLETED | 2025-05-02 | RE - PROGRAMMED | 25WA54 | D4089 | Warwick | Maple Grove | Glasshouse Lane | End of road
2025-04-22 | COMPLETED | 2025-05-02 | RE - PROGRAMMED | 25WA55 | D4134 | Warwick | Lilac Grove | Leyes Lane | Parkfield Drive
2025-04-22 | COMPLETED | 2025-05-06 | RE - PROGRAMMED | 25WA33 | D4559 | Leamington Spa | Priory Terrace | Park Hill | School Access
2025-04-22 | COMPLETED | 2025-05-06 | RE - PROGRAMMED | Remedial site |  | Leamington Spa | Swadling Street | Woodloes Avenue North | End of road
2025-04-22 | COMPLETED | 2025-05-06 | RE - PROGRAMMED | Remedial site |  | Leamington Spa | Sargeaunt Street | Dencer Drive | Glasshouse Lane
2025-04-22 | COMPLETED | 2025-05-06 | RE - PROGRAMMED | Remedial site |  | Leamington Spa | Clapham Street | Herberts Lane | Spring Lane
2025-04-22 | COMPLETED | 2025-05-06 | RE - PROGRAMMED | Remedial site |  | Leamington Spa | Clapham Terrace | Woodcote Lane | All
2025-04-22 | COMPLETED | 2025-05-06 | RE - PROGRAMMED | 25WA34 | D4354 | Leamington Spa | Hellidon Close | Glasshouse Lane | End
2025-04-22 | COMPLETED | 2025-05-06 | RE - PROGRAMMED | 25WA35 | D4353 | Leamington Spa | Napton Drive (part) | Riversleigh Road | end of cul-de-sac
2025-04-22 | COMPLETED | 2025-05-06 | RE - PROGRAMMED | 25WA39 | D4618 | Leamington Spa | Cundall Close | Old Milverton Road | End of road
2025-04-22 | COMPLETED | 2025-05-06 | RE - PROGRAMMED | 25WA40 | D4719 | Leamington Spa | Swain Crofts | Old Milverton Road | End of road
2025-04-23 | COMPLETED | 2025-05-07 | RE - PROGRAMMED | 25WA16 | D7368 | Kenilworth | Tintagel Grove | Old Milverton Road | End of road
2025-04-23 | COMPLETED | 2025-05-07 | RE - PROGRAMMED | 25WA17 | D7078 | Kenilworth | Dunvegan Close | Old Milverton Road | End of cul-de-sac
2025-04-23 | COMPLETED | 2025-05-07 | RE - PROGRAMMED | 25WA18 | D7106 | Kenilworth | Inveraray Close | Emmott Drive | End of cul-de-sac
2025-04-23 | COMPLETED | 2025-05-07 | RE - PROGRAMMED | 25WA29 | D7381 | Kenilworth | Caista Grove | The Chantry | End of road
2025-04-23 | COMPLETED | 2025-05-07 | RE - PROGRAMMED | 25WA15 | D7360 | Kenilworth | Lindisfarne Drive | Spinney Hill | End of road
2025-04-24 | COMPLETED | 2025-05-06 | RE - PROGRAMMED | 25WA38 | D4613 | Leamington Spa | Craig Close | Mill Street | Church Street
2025-04-24 | COMPLETED | 2025-05-06 | RE - PROGRAMMED | 25WA37 | D4717 | Leamington Spa | Kilby Grove | Kennan Ave | Lee road
2025-04-24 | COMPLETED | 2025-05-07 | RE - PROGRAMMED | 25WA36 | D4654 | Leamington Spa | Emmott Drive | Kennan Ave | Bury Road
2025-04-24 | COMPLETED | 2025-05-07 | RE - PROGRAMMED | 25SD05 | D6369 | Bishops Itchington | St Michaels Close | Clapham Terrace | End Of Road
2025-04-24 | COMPLETED | 2025-05-07 | RE - PROGRAMMED | 25SD39 | D2353 | Ufton | White Hart Lane | Canal Bridge By Nimrod Cottage | End of Road
2025-04-24 | COMPLETED | 2025-05-07 | RE - PROGRAMMED | 25SD91 | D6055 | Harbury | PINEHAM AVENUE | Napton Drive | End of cul-de-sac
2025-04-24 | COMPLETED | 2025-05-07 | RE - PROGRAMMED | 25SD93 | D6380 | Bishops Itchington | CENTRAL DRIVE | Junction at no-33 | End of road
2025-04-24 | COMPLETED | 2025-05-07 | RE - PROGRAMMED | 25SD97 | D6061 | Harbury | MANOR ROAD | Emmott Drive | End of cul-de-sac
2025-04-24 | COMPLETED | 2025-05-07 | RE - PROGRAMMED | 25SD103 | D6382 | Bishops Itchington | OLD ROAD / POPLAR ROAD | Emmott Drive | End of cul-de-sac
2025-04-25 | COMPLETED | 2025-05-07 | RE - PROGRAMMED | 25SD04 | D6381 | Bishops Itchington | Poplar Road | Emmott Drive | End of road
2025-04-25 | COMPLETED | 2025-05-07 | RE - PROGRAMMED | 25SD101 | D2660 | Ufton | ST MICHAELS CLOSE | Kilby Grove | Swain Crofts
2025-04-25 | COMPLETED | 2025-05-08 | PLANNED | 25WA47 | C36 | Offchurch | Welsh Road | Fisher Road | Chapel Street
2025-04-25 | COMPLETED | 2025-05-08 | PLANNED | 25SD85 | D2343 | Long Itchington | WULFSTAN DRIVE | Plough lane | End
2025-04-25 | COMPLETED | 2025-05-08 | PLANNED | 25SD86 | D2389 | Southam | PARKFIELDS | White Hart Pub Entrance | Southam Road
2025-04-25 | COMPLETED | 2025-05-08 | PLANNED | 25SD87 | D2388 | Southam | HORSEWELL | South Parade | End of road
2025-04-25 | COMPLETED | 2025-05-08 | PLANNED | 25SD88 | D6923 | Southam | SPRINGFIELD GROVE | Ladbrooe Road | Old Road
2025-04-25 | COMPLETED | 2025-05-08 | PLANNED | 25SD96 | D2401 | Southam | HEATHER CLOSE | Park Lane | Bush Heath lane
2025-04-26 | COMPLETED | N/A |  | Remedial site |  | Nuneaton | Cedar Road ( various sections ) | Southam Road | Harbury Road
2025-04-26 | COMPLETED | N/A |  | Remedial site |  | Chorley | Tamworth Road ( various sections ) | Ivy Villa | Ladbroke Road
2025-04-26 | COMPLETED | N/A |  | Remedial site |  | Leamington Spa | Southam Road | Radford Road | S/C after last bend towards Fosseway
2025-04-26 | COMPLETED | 2025-05-06 | PLANNED | 25WA46 | D4369 | Leamington Spa | Clarendon Avenue | Jnc Stockton Road | ALL
2025-04-26 | COMPLETED | 2025-05-06 | PLANNED | 25WA31 | A452 | Leamington Spa | Adelaide Road | Jnc Little Park | End - include Horeswell
2025-04-27 | COMPLETED | N/A |  | Remedial site |  | Stratford | Wixford | Jnc Parkfields | End
2025-04-27 | COMPLETED | 2025-05-09 | PLANNED | Remedial site |  | Stratford | Great Wolford | Jnc Linley road | End
2025-04-27 | COMPLETED | N/A |  | 25SD38 | C137 | Tanworth In Arden | Tom Hill | Jnc Stowe drive | End
2025-04-28 | COMPLETED | 2025-05-08 | PLANNED | 25SD89 | D2394 | Southam | BRIDGE END | Coventry Street | End
2025-04-28 | COMPLETED | 2025-05-08 | PLANNED | 25SD99 | D2379 | Southam | HURST ROAD | O/S No 52 | Jnc Beech Close
2025-04-28 | COMPLETED | 2025-05-08 | PLANNED | 25SD100 | D2405 | Southam | WATTONS LODGE | Wattons Lane | End
2025-04-28 | COMPLETED | 2025-05-08 | PLANNED | 25SD13 | D6386 | Fenny Compton | Berry Meadow | Station Road | End
2025-04-28 | COMPLETED | 2025-05-08 | PLANNED | 25SD94 | D2233 | Warmington | RECTORY CLOSE | Vilage Road | End
2025-04-28 | COMPLETED | 2025-05-08 | PLANNED | 25SD95 | D6392 | Fenny Compton | GRANTS CLOSE | Avon Dassett Road | All
2025-04-28 | COMPLETED | 2025-05-08 | PLANNED | 25SD90 | D6401 | Northend | HILL CLOSE | Rowan House | Highfield
2025-04-28 | COMPLETED | 2025-05-08 | PLANNED | 25SD104 | D6400 | North End | THE PREBEND | Combrook Road | To End
2025-04-29 | COMPLETED | 2025-05-09 | PLANNED | 25SD09 | D6366 | Combrook | School Lane | Combrook Road | To End
2025-04-29 | COMPLETED | 2025-05-09 | PLANNED | 25SD10 | D6350 | Combrook | Spring Lane | Jnct The Prfebend | All
2025-04-29 | COMPLETED | 2025-05-08 | PLANNED | 25SD22 | D6438 | Kineton | Castle Road | Top Street | End
2025-04-29 | COMPLETED | 2025-05-09 | PLANNED | 25SD08 | D6364 | Combrook | Church Hill - Combrook Road | Barford Road | End of road
2025-04-29 | COMPLETED | 2025-05-10 | PLANNED | 25WA01 | D6719 | Barford | Ryland Road | Warwick Road | End
2025-04-29 | COMPLETED | 2025-05-10 | PLANNED | Remedial site |  | Leamington Spa | Franklin Road | Queen Elizabeth Road | Copper Beach Road
2025-04-30 | PLANNED | 2025-05-10 | PLANNED | 25WA02 | D6012 | Barford | Church Lane | M6 over bridge | WCC/CCC Boundary
2025-04-30 | PLANNED | 2025-05-10 | PLANNED | 25SD77 | D6357 | Lighthorne | MOUNTFORD RISE - EVENS | Offchurch Lane | 30mph Speed Limit Gateway
2025-04-30 | PLANNED | 2025-05-10 | PLANNED | 25SD78 | D6357 | Lighthorne | MOUNTFORD RISE - ODDS | Clarendon Place | S/C outside petrol station
2025-04-30 | PLANNED | 2025-05-10 | PLANNED | 25SD79 | D6356 | Lighthorne | POST OFFICE LANE | Mini island | Pedestrain crossing just beyond York Road
TBA | PLANNED | N/A |  | Remedial site |  | Stratford | Dorsington /Long Marston | Jnc Vicarge Hill | All
TBA | PLANNED | N/A |  | Remedial site |  | Stratford | Lower Quinton | Ennister Lane | Evesham Road
2025-04-30 | PLANNED | 2025-05-10 | PLANNED | 25SD84 | D6359 | Lighthorne | OLD SCHOOL LANE | Barton On Heath road | Little Wolford Road
2025-04-30 | PLANNED | 2025-05-10 | PLANNED | 25SD45 | D6343 | Wellesbourne | Westfield Crescent | Broad Lane | Butts Lane
2025-04-30 | PLANNED | 2025-05-10 | PLANNED | 25SD106 | D9018 | Wellesbourne | PEMBROKE GARDENS | Heathcote Road | Moorhill Road
2025-04-30 | PLANNED | 2025-05-10 | PLANNED | 25SD46 | D6333 | Wellesbourne | Linden Ave | Start of cul-de-sac | End of cul-de-sac
2025-04-30 | PLANNED | 2025-05-10 | PLANNED | 25SD47 | D6334 | Wellesbourne | Sycamore Close | Bishops Hill | End
2025-04-30 | PLANNED | 2025-05-10 | PLANNED | 25SD92 | D6331 | Wellesbourne | BROOKSIDE AVENUE | Bishops Hill | End
2025-04-30 | PLANNED | 2025-05-10 | PLANNED | 25SD98 | D6332 | Wellesbourne | ASH TREE CLOSE | Bishops Hill | End
2025-04-30 | PLANNED | N/A |  | Remedial site |  | Shrewley | The Cumsey | The Green | End
2025-05-01 | PLANNED | N/A |  | Remedial site |  | Chessetts Wood | Bakers Lane | C72 Stratford Road | Entire Length
2025-05-01 | PLANNED | 2025-05-11 | PLANNED | 25SD59 | D5508 | Norton Lyndsey | Norton Lea | Dovehouse Drive | All
2025-05-01 | PLANNED | 2025-05-11 | PLANNED | 25SD65 | D5582 | Bearley | GREENSWOOD | Nebsworth Lane | Larkstone Cottage
2025-05-01 | PLANNED | 2025-05-11 | PLANNED | 25SD67 | D5249 | Claverdon | COMMON LANE | Willow Drive | Sycamore Close
2025-05-01 | PLANNED | 2025-05-11 | PLANNED | 25WA49 | D5115 | Rowington | St Laurence Close | Linden Avenue | All
2025-05-01 | PLANNED | 2025-05-11 | PLANNED | 25WA50 | D5054 | Rowington | Yew Tree Close | Willow Drive | End
2025-05-01 | PLANNED | 2025-05-11 | PLANNED | 25WA58 | D5094 | Hatton Station | STATION ROAD Service Road | Brookside Avenue | End
2025-05-01 | PLANNED | 2025-05-11 | PLANNED | 25SD29 | D5330 | Snitterfield | Hales Close | Dorsington Road | Welford Road
2025-05-01 | PLANNED | 2025-05-12 | PLANNED | 25SD62 | D5445 | Bishopton | BURTON FARM ROAD | Main Street | St Swithens Drive
2025-05-02 | PLANNED | 2025-05-11 | PLANNED | 25SD21 | D6535 | Ilmington | Downs Hill Road | Canal Bridge | O/S No 17
2025-05-02 | PLANNED | N/A |  | Remedial site |  | Norton Lyndsey | Wolverton Road | Back lane | Common Lane
2025-05-06 | PLANNED | 2025-05-12 | PLANNED | 25SD71 | D5125 | Henley | CASTLE ROAD / CASTLE CLOSE | Jnc Wolverton Road | End
2025-05-06 | PLANNED | 2025-05-12 | PLANNED | 25SD18 | D5241 | Henley In Arden | Chingley Bank | Jnc Bearley Green | End
2025-05-06 | PLANNED | 2025-05-12 | PLANNED | 25SD58 | D8035 | Henley | Whitley Hill | Pippenford | Lye Green Lane
2025-05-06 | PLANNED | 2025-05-12 | PLANNED | 25SD75 | D5586 | Wootton Wawen | GLEBE CLOSE | Mill Lane | End of cul-de-sac
2025-05-06 | PLANNED | 2025-05-12 | PLANNED | 25SD56 | D8047 | Henley | Prince Harry road | Station Lane | End of cul-de-sac
2025-05-06 | PLANNED | 2025-05-12 | PLANNED | 25SD70 | D5239 | Henley | RIVERSIDE GARDENS | D5093 Station Road | End
2025-05-06 | PLANNED | 2025-05-12 | PLANNED | 25SD60 | D5592 | Ullenhall | Crowley close | Jnc Arden Road | Castle close
2025-05-06 | PLANNED | 2025-05-12 | PLANNED | 25SD17 | D5224 | Henley In Arden | Glenhurst Road | Wolverton Road | End
2025-05-06 | PLANNED | 2025-05-12 | PLANNED | 25SD19 | D5237 | Henley In Arden | Rose Avenue | Jnc A46 | Bishopton grange
2025-05-06 | PLANNED | 2025-05-14 | PLANNED | Remedial site |  | Polesworth | Bridge Street | Arden Road | End
2025-05-06 | PLANNED | N/A |  | 25NW23 | B4114 | Shustoke | Church road / Coleshill road | Jnc A4189 Warwick Road | End
2025-05-06 | PLANNED | 2025-05-14 | PLANNED | 25NW26 | D124 | Baddersley | ST NICHOLAS ESTATE | Jnc A3400 Stratford Road | End
2025-05-06 | PLANNED | 2025-05-14 | PLANNED | 25NW31 | D182 | Atherstone | SOUTH STREET | School Road | Wolverton
2025-05-06 | PLANNED | 2025-05-14 | PLANNED | 25NB06 | D1495 | Whitleford | Barons Croft | Jnc A4189 Warwick road | End
2025-05-06 | PLANNED | 2025-05-14 | PLANNED | 25NB08 | D1012 | Whittleford | Portland Drive | Jnc Meadow road | O/S 27
2025-05-07 | PLANNED | 2025-05-09 | PLANNED | 25SD57 | D5029 | Tanworth In Arden | Bellfield | Ullenhall Lane | End
2025-05-07 | PLANNED | N/A |  | Remedial site |  | Ullenhall | Gorcote Hill | Jnc Church Hill | End
2025-05-07 | PLANNED | 2025-05-13 | PLANNED | 25SD31 | D5164 | Studley | St Asaphs Avenue | St Judes Avenue | Corbizum Avenue
2025-05-07 | PLANNED | 2025-05-13 | PLANNED | 25SD32 | D5163 | Studley | Corbizum Avenue | Augustine Avenue | St Judes Ave
2025-05-07 | PLANNED | 2025-05-13 | PLANNED | 25SD33 | D5162 | Studley | Augustine Avenue | St Judes Avenue | St Judes Ave
2025-05-07 | PLANNED | 2025-05-13 | PLANNED | 25SD34 | D5192 | Studley | The Cloisters | Augustine Avenue | End
2025-05-07 | PLANNED | 2025-05-13 | PLANNED | 25SD35 | D5186 | Studley | Allendale Crescent | New Road | ALL
2025-05-07 | PLANNED | 2025-05-13 | PLANNED | 25SD61 | D5183 | Studley | Rowland Avenue | Jnc High Street | End
2025-05-07 | PLANNED | 2025-05-13 | PLANNED | 25SD66 | D5184 | Studley | GREEN CLOSE | Watts Lane | End of Road
2025-05-07 | PLANNED | N/A |  | 25NB02 | D1454 | Griff | Gipsy lane | Jnc Toms Town Lane | Allendale Crescent
2025-05-07 | PLANNED | N/A |  | 25NB03 | A4254 | Nuneaton | Eastboro Way | Jnc Rowland Avenue | End
2025-05-07 | PLANNED | N/A |  | 25RU22 | D2005 | Wolvey | Bazzard Road | Alcester Road North | Alcester Road South
2025-05-08 | PLANNED | 2025-05-14 | PLANNED | 25SD36 | D5187 | Studley | Park Avenue | A435 Alcester Road | End
2025-05-08 | PLANNED | 2025-05-13 | PLANNED | 25SD37 | D5190 | Studley | Morgan Close | Castle Road | End
2025-05-08 | PLANNED | 2025-05-13 | PLANNED | 25SD55 | D8031 | Studley | Riverside | Littlewood Green | End
2025-05-08 | PLANNED | 2025-05-14 | PLANNED | 25SD63 | D5173 | Studley | THE GROVE | B4093 Reditch road | End
2025-05-08 | PLANNED | 2025-05-14 | PLANNED | 25SD64 | D5198 | Studley | CRENDON CLOSE | Jnc Littlewood Green | End Of Road
2025-05-08 | PLANNED | 2025-05-14 | PLANNED | 25SD68 | D5175 | Studley | LORDS LANE | Jnc High Street | End
2025-05-08 | PLANNED | 2025-05-14 | PLANNED | 25SD69 | D5197 | Studley | ALBERT CLOSE | Jnc Castle Road | End
2025-05-08 | PLANNED | 2025-05-13 | PLANNED | 25SD72 | D5148 | Studley | WICKHAM ROAD | Jnc Manor road | End
2025-05-08 | PLANNED | 2025-05-13 | PLANNED | 25SD73 | D5152 | Studley | ALBURY ROAD | Jnc High Street | Jnc Alcester Road
2025-05-08 | PLANNED | 2025-05-14 | PLANNED | 25SD74 | D5155 | Studley | MARBLE ALLEY
2025-05-08 | PLANNED | N/A |  | 25RU24 | B4112 | Withybrook | Rugby Road | FROM | TO
2025-05-08 | PLANNED | N/A |  | 25RU21 | B4428 | Stretton-under-Fosse | Main Street/Lutterworth Road | High Street | B5000 Grendon Road
2025-05-09 | RE-PROGRAMMED | 2025-05-15 | RE-PROGRAMMED | 25WA08 | D7077 | Kenilworth | Denewood Way | SC on Coleshill Road | SD Junction Castle lane
2025-05-09 | RE-PROGRAMMED | 2025-05-15 | RE-PROGRAMMED | 25WA19 | D7044 | Kenilworth | Park Hill (Service Road) | Boot Hill | Hill Top
2025-05-09 | RE-PROGRAMMED | 2025-05-15 | RE-PROGRAMMED | 25WA63 | D7061 | Kenilworth | PARKFIELD DRIVE | Margaret Rd | Witherley Rd
2025-05-09 | RE-PROGRAMMED | 2025-05-15 | RE-PROGRAMMED | 25WA53 | D4060 | Warwick | Sutherland Close | Portland Drive | End
2025-05-09 | RE-PROGRAMMED | 2025-05-15 | RE-PROGRAMMED | 25WA59 | D7066 | Kenilworth | LEYES LANE | Sherbourne Avenue | Sherbourne Avenue
2025-05-09 | RE-PROGRAMMED | 2025-05-15 | RE-PROGRAMMED | 25WA61 | D7035 | Kenilworth | ARTHUR STREET | B4113 Coventry Road | New Surface
2025-05-09 | RE-PROGRAMMED | 2025-05-15 | RE-PROGRAMMED | 25WA65 | D5079 | Leek Wootton | WALLER CLOSE | Townsend Dr Roundabout | New Surface
2025-05-09 | RE-PROGRAMMED | 2025-05-15 | RE-PROGRAMMED | 25WA66 | D7400 | Kenilworth | EDWARDS GROVE | B4109 Bulkington Road | B4114 Lutterworth Road
2025-05-09 | PLANNED | N/A |  | 25RU13 | A428 | Church Lawford | Coventry Road | S/C near new roundabout | B4109 Church Hill/Leicester Road
2025-05-09 | PLANNED | N/A |  | 25RU18 | A428 | Hillmorton | Crick Road | S/C at Main Street | S/C near culvert
2025-05-09 | PLANNED | 2025-05-14 | PLANNED | 25RU20 | D3152 | Newbold | Oliver street | S/C South of Stretton Village | S/C at Brinklow Village Gateway
2025-05-09 | PLANNED | N/A |  | 25RU14 | B4453 | Bourton and Draycote | Straight Mile | Red panel at entrance to Village | Gas Station beyond Skew bridge
2025-05-10 | PLANNED | N/A |  | 25SD50 | A429 | Stretton On Fosse | Fosse Way | Kilsby Lane | New surface joint after second Railway Bridge
2025-05-10 | PLANNED | N/A |  | 25SD51 | A429 | Shipston | Fosse Way | Lawford Road | Corporation St
2025-05-10 | PLANNED | N/A |  | 25SD52 | A429 | Tredington | Fosse Way | D2174 BLUE BOAR TO DRAYCOTE | Main St
2025-05-10 | PLANNED | N/A |  | 25SD07 | B4086 | Charlecote | Wellesbourne Road / Stratford Road | Ullenhall Road end of existing dressing | Roundabout Mappleborough Green
2025-05-11 | PLANNED | N/A |  | 25NW01 | A446 | Coleshill | Stonebridge | Ullenhall Road end of existing dressing | Ullenhall Road end of existing dressing
2025-05-11 | PLANNED | N/A |  | 25NW02 | A446 | Coleshill | Stonebridge | Northfield Farm | Rowborough Farm
2025-05-11 | PLANNED | N/A |  | 25NW03 | A446 | Coleshill | Stonebridge | Surface Change Nr Portabellow X-rds | Surface Chane Nr Darlingscote X-Rds
2025-05-11 | PLANNED | N/A |  | 25NW04 | A446 | Coleshill | Stonebridge | Jnc Blackwell Road | Electric Distribution Centre
2025-05-11 | PLANNED | 2025-06-01 | PLANNED | 25RU15 | A426 | Rugby Unparished Area | Newbold Road | Halford Island | A422 Banbury Road Ettington
2025-05-12 | PLANNED | N/A |  | Remedial site |  | Napton | Daventry Road | Kissing Tree Lane | Charlecote Road Cross Roads
2025-05-13 | PLANNED | N/A |  | 25WA48 | B4439 | Rowington | Old Warwick Road | Coleshill Heath Road Island | Police Island
2025-05-13 | PLANNED | TBC |  | 25WA52 | C32 | Stoneleigh | Stonleigh Road | Police Island | Coleshill Heath Road Island
2025-05-13 | PLANNED | TBC |  | Remedial site |  | Burton Green | Red Lane | Police Island | Gilson Lane Island
2025-05-13 | PLANNED | N/A |  | 25WA51 | C25 | Shrewley | Five Ways Road | Gilson Lane Island | Police Island
2025-05-14 | PLANNED | N/A |  | 25SD23 | C39 | Langley Green | Langley Road | Bridge before roundabout | Evreux Way roundabout
2025-05-14 | PLANNED | N/A |  | 25W01 | A4177 | Hatton | Birmingham Road | M45 Jnct | Longdown Lane
2025-05-15 | PLANNED | N/A |  | 25SD16 | C39 | Henley In Arden | Salters lane | Napton Village | Canal Bridge west side of Napton
2025-05-15 | PLANNED | N/A |  | 25SD02 | D5321 | Bearley | Bearley Road | STW pumping station | s/c at access to "High Chimneys Cottage
2025-05-16 | PLANNED | TBC |  | 25WA32 | A425 | Leamington Spa | Radford Road | S/C change at A46 island works | County Bounday adj 35 Stoneleigh Road
2025-05-16 | PLANNED | N/A |  | 25SD25 | C96 | Moreton Padox | Wellesbourne Road | Burrow Hill Lnae | O/S Thuris House
2025-05-16 | PLANNED | TBC |  | 25SD43 | C72 | Wellesbourne | Bridge Street / Ettington Road | Case Lane | Old Warwick Road
2025-05-16 | PLANNED | TBC |  | 25SD44 | C72 | Wellesbourne | Dove House Drive | Stratford Road | Saddlebow Lane
2025-05-17 | PLANNED | N/A |  | 25SD40 | A4189 | Ullenhall | Henley Road | Charringworth Drive | Brownley Green Lane
2025-05-17 | PLANNED | N/A |  | 24SD107 | A4189 | Ullenhall | Henley Road | Bearley Road | Newnham Lane
2025-05-17 | PLANNED | N/A |  | 25SD53 | B4455 | Ettington | Fosse way | Old Snitterfield Road | 30mph Sign Sniterfield
2025-05-18 | PLANNED | N/A |  | 25NW06 | B4111 | Hartshill | Nuneaton Road 65 PSV | no-186 | 30mph signs just before canal bridge
2025-05-18 | PLANNED | N/A |  | 25NW18 | B4111 | Mancetter | Nuneaton Road | B4455 Fosse way | Treetops
2025-05-18 | PLANNED | N/A |  | 25WA03 | C138 | Budbrooke | Old Budbrooke Road | Warwick road Gyratory | A429
2025-05-18 | PLANNED | N/A |  | 25WA04 | C138 | Hampton Magna | Old Budbrooke Road | Loxley Road | Loxley Road
2025-05-18 | PLANNED | N/A |  | 25SD24 | A425 | Lower Shuckburgh | Daventry Road | Approx 50m from jnc Atherstone Road | Start of the bridge
2025-05-18 | PLANNED | N/A |  | 25SD30 | D6713 | Southam | Westfield Road | Surface Course Joint Brooklands Farm | 50m from Jnc Woodford Lane
2025-05-19 | PLANNED | N/A |  | 25SD49 | A3400 | Long Compton | Shipston Road | A4177 Birmingham Road | Traffic Lights Warwick Parkway
2025-05-19 | PLANNED | N/A |  | 25SD15 | C72 | Goldicote | Blue Lane / Goldicote Road | Damson Road | Woodway Lane
2025-05-20 | PLANNED | N/A |  | 25SD48 | A3400 | Atherstone on Stour | Shipston Road | Canal Bridge By Nimrod Cottage | County Boundary
2025-05-20 | PLANNED | N/A |  | 25SD01 | C72 | Alderminster | New Road | Kineton Road | End
2025-05-20 | PLANNED | N/A |  | 25SD06 | D6564 | Blackwell | Ilmington Road | 30mph signs at end of village | County Boundary
2025-05-21 | PLANNED | N/A |  | 25SD54 | A422 | Oxhill | Banbury Road | A422 Banbury Road | Hillside Manor
2025-05-21 | PLANNED | N/A |  | 25SD20 | C48 | Ilmington | Campden Hill / Nebsworth Lane | Surface Change near Springfield House | Jnc to Atherstone on Stour
2025-05-22 | PLANNED | N/A |  | 25SD14 | B4100 | Gaydon | Banbury Road | A422 Banbury road | A3400 Shipston Road
2025-05-22 | PLANNED | N/A |  | 25SD27 | D6429 | Radway | Farnborough Road | Distilliers Cottage | Junction
2025-05-22 | PLANNED | N/A |  | 25SD41 | C11 | Warmington | Mollington Lane | End of existing Surface Dressing | C54 Tysoe road X-Rds
2025-05-22 | PLANNED | N/A |  | 25SD42 | C11 | Shotteswell | Mollington Road | Back Street | WCC Boundary
2025-05-22 | PLANNED | 2025-06-01 | PLANNED | 25SD82 | C96 | Lighthorne | CHESTERTON ROAD | Surface Joint at Gaydon Roundabout | Surface Change at Speed Limit
2025-05-22 | PLANNED | 2025-06-01 | PLANNED | 25SD83 | C96 | Lighthorne | WELLESBOURNE ROAD | B4086 Banbury Road | Langdon Lane
2025-05-23 | PLANNED | N/A |  | 25SD03 | C143 | Bishops Itchington | Plough Lane | Village Road | WCC Boundary
2025-05-27 | PLANNED | N/A |  | 25RU16 | A45 | Dunchurch | Daventry Road | WCC Boundary | Access to Sewage works
[8 empty] | B4100 Banbury Road | The Green
Maintrain Programme 2025/26 | [7 empty] | The Green | 30mph Speed Limit Gateway
S/D TARGET DATE | STATUS | KIELEY LOCK DATE | STATUS | REF # | ROAD NO. | PARISH | ROAD NAME | B4451 Stockton Road | Harbury lane