## Sheet1
Main Train Programme
TARGET DATE | STATUS | REF # | ROAD NO. | PARISH | ROAD NAME | FROM | TO
2024-05-19 | Complete | SD9 | C120 | Atherstone | Coleshill Road | WOODSIDE COTTAGES | Twenty One Oaks
2024-05-19 | Complete | SD12 | C6 | Atherstone | Monks Park Lane | FORESTRY GATE NO. 10 | Transmitter Station
2024-08-28 | Complete | SD13 | C78 | Polesworth | Bridge Street | C5 HIGH STREET | B5000 Grendon Road
2024-05-14 | Complete | SD3 | A51 | Kingsbury | Coventry Road | Trinity rd | Island
Wednesday 15th & Thursday 16th May | Complete | SD5 | A4091 | Kingsbury | Tamworth Road | A4091 (BOTH SIDES??) | BELFRY ISLAND
2024-05-17 | Complete | SD11 | B4114 | Furnace End | Nuneaton Road (Furnace Lane) | B4098 COVENTRY ROAD | Sadlers Meadow
2024-05-18 | Complete | SD14 | A444 | Nuneaton | Coton Road | Coventry road | Coton Arches
2024-05-17 | Complete | SD1 | B4111 | Mancetter | Harpers Lane | A5 watling st | Mill Lane
2024-05-18 | Complete | SD10 | C126 | Arley | Ansley Lane | ARLEY PARISH BOUNDARY BOURNE BROOK to Church lane | Church Lane
| CANCELLED - NOW 2025/26 | SD23 | A426 | Rugby | Newbold Road | Poice station island | Railway Bridge
2024-05-29 | Complete | SD20 | A4071 | Rugby | Western Relief Road | Lawford rd | End of Duals
2024-05-18 | Complete | SD19 | D1794 | Exhall | Bayton Road | Coventry rd | Stephenson Road
2024-05-18 | Complete | SD17 | B4113 | Exhall | Coventry Road | Blackhorse rd | Hayes lane
2024-05-19 | Complete | SD7 | C18 | Kingsbury | Trinity Road | M42 JUNCTION 10 ISLAND | C122 Trinity Road
2024-05-19 | Complete | SD6 | A4097 | Kingsbury | Kingsbury Road | DUNTON HALL roundabout | Blackgeaves Lane
2024-05-19 | Complete | SD2 | B4114 | Coleshill | Birmingham Road (Coleshill) | A446 | Parkfield Road
2024-05-19 | Complete | SD15 | A47 | Nuneaton | Hinckley Road | Eastboro way | Higham Lane
2024-05-20 | Complete | SD8 | C78 | Exhall | Bennits Road North | GROVE FARM | WCC Boundary
2024-05-20 | Complete | SD18 | C18 | Exhall | Goodyears end | Smarts road | Newcomen Road
2024-05-20 | Complete | SD16 | B4029 | Nuneaton | Bulkington Road | West avenue | Canal Bridge
2024-05-20 | Complete | SD25 | B4109 | Wolvey | Wolvey Road | Bazzard Road | Elgin R M Ltd
2024-05-21 | Complete | SD22 | A428 | Rugby | Hillmorton Road | Hillmorton island | Boundary Road
2024-05-21 | Complete | SD27 | B4455 | Wolston | Fosse way 1 | Coventry Rd | A45
2024-05-18 | Complete | SD28 | B4642 | Rugby | Bilton Road | RUSSELSHEIM WAY | Bloxham Gardens
2024-06-09 | Complete | SD26 | B4455 | Brinklow | Queens Road | Rugby rd | King Newham Road
2024-06-08 | Complete | SD31 | A452 | Bishops Tachbrook | Banbury Rd | Roundabout | Mallory Road
2024-06-09 | Complete | SD72 | C43 | Harbury | Harbury Lane | S/C Fosse Way | Temple End
2024-05-31 | Complete | SD77 | C46 | Long Marston | Mickleton Road | Surface Change | S/C before Bridge
2024-08-21 | Complete | SD78 | C | Wixford | Ennister Lane | Evesham Road | Wixford Road
2024-05-30 | Complete | SD61 | A422 | Arrow | Arrow Lane | A422 | Surface Change
2024-08-21 | CANCELLED - NOW 2025/26 | SD83 | A448 | Studley | The Slough | Green Lane | Speed/ Surface Change
2024-05-30 | Complete | SD82 | B4093 | Studley | Redditch Road | Station Road | Green Lane
2024-05-24 | Complete | SD59 | A4189 | Ullenhall | Redditch Road (LINKED WITH SD60) | S/C outside Aibean Grange | Church Rd
2024-05-24 | Complete | SD60 | A4189 | Henley in Arden | Henley Road (LINKED WITH SD 59) | S/C past Henley Road | Mays Hill
| CANCELLED - NOW 2025/26 | SD62 | A422 | Stratford | Alcester Rd | Alcester Road Roundabout | Church Lane
2024-08-22 | Complete | SD37 | C25 | Shrewley | The Cumsey | Back Lane | Common Lane
2024-06-04 | Complete | SD57 | A3400 | Treddington | Stratford Road | Farm Access | jnct Mill Lane
| CANCELLED - NOW 2025/26 | SD58 | A3400 | Shipston on Stour | Stratford Road | Speed Limit | Telegraph Street
2024-06-04 | Complete | SD63 | A429 | Wellesbourne | Ettington Road | o/s Track for Woodfield Farm | Speed Change
2024-05-29 | Complete | SD69 | C54 | Little Kineton | Tysoe Road | Kineton Road | Jct A422
2024-05-30 | Complete | SD74 | B4086 | Combrook | Compton Hill | o/s Park Farm | s/c by Speed Limit Kineton
2024-05-29 | Complete | SD75 | B4100 | Gaydon | Banbury Rd | Speed Limit | 160m NE of Railway Bridge
2024-05-23 | Complete | SD79 | C33 | Napton | Napton Road | Tomlow Road | Station Road
2024-05-23 | Complete | SD73 | B4451 | Southam | Kineton Road | 200m NE of 'Field Farm' | Harbury Road
2024-05-23 | Complete | SD80 | D2266 | Napton | Tomlow Road | A425 | Calias Lane
2024-05-31 | Complete | SD67 | A4390 | Stratford | Trinity Way | Banbury Road Roundabout | Wordsworth Avnue
2024-05-31 | Complete | SD56 | A3400 | Bearley | Stratford Road | Jct with Langley Road | Jnct with Snitterfield Rd
2024-06-09 | Complete | SD47 | C39 | Norton Lindsey | Wards Hill (WOLVERTON ROAD) | Curlieu Lane | Brittons Lane
2024-08-21 | CANCELLED - NOW 2025/26 | SD32 | B4101 | Hockley Heath | Spring Lane | County Boundary | Tithe Barn Lane
| CANCELLED - NOW 2025/26 | SD53 | A452 | Kenilworth | Leamington Road | Thickthorn Island | Thickthorn Island
2024-06-02 | Complete | SD64 | A435 | Studley | Alcester Rd | o/s The Bell | o/s 81
2024-06-02 | Complete | SD65 | A435 | Studley | Alcester Rd | Toms Town Lane | Bromsgrove Road
2024-06-03 | Complete | SD55 | A3400 | Hockley Heath | Stratford Road | Wharf Lane | Speed Change o/s Oakleigh
2024-06-03 | Complete | SD33 | B4101 | Hockley Heath | Aylesbury Road | o/s 86 | o/s 232
2024-06-03 | Complete | SD35 | C36 | Lillington | Westhill Road | Stoneleigh Road | Leicester Lane
2024-06-03 | Complete | SD40 | B4113 | Blackdown | Stoneleigh Road | Sandy Lane | Bericote Road
2024-06-03 | Complete | SD51 | B4455 | Eathorpe | Fosse Way | Old Fosse Way | Long Itchington Road
2024-06-03 | Complete | SD87 | B4455 | Hunningham | Fosse Way | Orchard House | Long Itchington Road
2024-08-28 | Completed | SD52 | C15 | Burton Green | Red Lane | Burrow Hill Lane | o/s "Thuris"
2024-06-04 | Complete | SD34 | B4103 | Kenilworth | Clinton Lane (LINKED WITH 24S85) | Jct Castle Green | Jct Beehive Hill
2024-06-04 | Complete | SD38 | A452 | Kenilworth | Birmingham Road (LINKED WITH 24S86) | Beehive Hill | Red Lane
2024-06-04 | Complete | SD39 | A452 | Kenilworth | Birmingham Road (LINKED WITH 24S85) | Red Lane | approx 75m after Drakeshill
Combi Programme
TARGET DATE | STATUS | REF # | ROAD NO. | PARISH | ROAD NAME | FROM | TO
2024-08-23 | Complete | SD29 | A429 | Warwick | St Nicholas Church St | Smith Street | Castle Hill
2024-08-27 | Complete | SD42 | D7177 | Cubbington | Pinehurst | Rugby Road | End of Road
2024-08-27 | Complete | SD43 | D4591 | Leamington Spa | Swadling Street | Kennan Avenue | Lee Road
2024-08-27 | Complete | SD44 | D4589 | Leamington Spa | Sargeaunt Street | Kennan Avenue | Bury Road
2024-08-27 | Complete | SD45 | D4727 | Leamington Spa | Clapham Terrace | Canal Bridge | End of road
2024-08-27 | Complete | SD46 | D4534 | Leamington Spa | Clapham Street | Clapham Terrace | End of road
2024-08-23 | Complete | SD50 | D4193 | Warwick | Church Street | St Marys Church | Jury Street
2024-08-22 | Complete | SD70 | C54 | Great Wolford | Barton on Heath Road | Little Wolford Road | The Green
2024-08-21 | Complete | SD71 | D5199 | Gorcott Hill | Gorcott Hill | Ullenhall Lane | Bears Cottage
2024-08-22 | Complete | SD76 | C | Stratford | Fordham Avenue | St Marys Road | Maidenhead Road
| CANCELLED - NOW 2025/26 | SD41 | D4369 | Leamington Spa | Clarendon Avenue | Clarendon Place | S/C outside petrol station
| CANCELLED - NOW 2025/26 | SD48 | A452 | Leam Spa | Adelaide Road | Mini island | Pedestrain crossing just beyond York Road
| CANCELLED - NOW 2025/26 | SD84 | D6564 | Blackwell | Ilmington Road | Distillers Cottage | Junction
2024-08-27 | Completed | SD49 | D4694 | Whitnash | Franklin Road | Heathcote Road | Moorhill Road
2024-08-28 | Completed |  |  | Nuneaton | Chase Close | Higham Lane | To End
W/C 9/9/2024 | Kiely Lock sealant | SD29 | A429 | Warwick | St Nicholas Church St | Smith Street | Castle Hill
W/C 9/9/2024 | Kiely Lock sealant | SD50 | D4193 | Warwick | Church Street | St Marys Church | Jury Street